## Slide 1: 7th PIRC Meeting (Virtual, 11th September 2020)
Progress Review Presentations

## Slide 2
Sr. No. | State | Page No.
 | Consolidate | 2-8
1. | Madhya Pradesh (WRD & NVDA) | 9-22
2. | Chhattisgarh | 23-27
3. | Maharashtra | 28-41
4. | Gujarat | 42-48
5. | Odisha | 49-56
6 | Karnataka | 57-66
7. | Goa | 67-73
8. | Rajasthan | 74-79
INDEX
7th PIRC Meeting (Virtual, 11th September 2020):
Progress Review Presentations
Sr. No. | State | Page No.
9. | Manipur | 80-83
10. | Assam | 84-97
11. | Telangana | 98-103
12. | AP | 104-112
13. | Bihar | 113-123
14. | Jharkhand | 124-127
15 | Uttar Pradesh | 128-134
16. | Punjab | 135-139
17. | J&K , Ladhakh | 140-157
18. | Kerala | 158-165

## Slide 3
Consolidate
Number of Projects : 91(99-8) Projects Included: 89 Projects Availing CA: 75 Projects Reporting Progress:56
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | CCA (in th. Ha.) | WUA (Nos)
Target | 18462.27 | 8298.96 | 4505.68 | 14673
Progress | 5312.7 | 2652.91 | 1487.88 | 8443
Physical Progress
7th PIRC Meeting (Virtual, 11th September 2020): Progress Review Presentations
Consolidate

## Slide 4
CCA Progress
Sr. No. | State | Balance CCA Target | CCA Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
1. | AP | 178.63 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 115.00
2. | Assam | 46.62 | 0.00 | 1.19 | 13.06 | 6.91 | 2.23 | 23.40 | 50.19 | 23.22
3. | Bihar | 32.24 | 2.25 | 5.49 | 4.00 | 2.63 | 1.16 | 15.52 | 48.14 | 15.72
4. | Chhattisgarh | 42.63 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 42.63
5. | Goa | 8.67 | 0.01 | 0.00 | 0.75 | 0.17 | 0.12 | 1.05 | 12.09 | 4.20
6 | Gujarat | 1363.86 | 385.33 | 290.06 | 260.17 | 1.59 | 1.46 | 938.61 | 68.82 | 0.00
7. | J&K | 2.46 | 0.00 | 0.00 | 1.03 | 0.66 | 0.00 | 1.69 | 68.86 | 0.36
8. | Jharkhand | 66.65 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 15.00
9. | Karnataka | 84.02 | 11.08 | 10.95 | 8.89 | 3.79 | 0.14 | 34.85 | 41.48 | 16.72
7th PIRC Meeting (Virtual, 11th September 2020): Progress Review Presentations
( Area in Th. Ha.)

## Slide 5
CCA Progress
Sr. No. | State | Balance CCA Target | CCA Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
10. | Kerala | 16.80 | 0.00 | 0.00 | 0.00 | 0.34 | 0.27 | 0.60 | 3.59 | 2.70
11. | Madhya Pradesh (WRD) | 311.26 | 71.83 | 73.64 | 37.64 | 21.20 | 0.39 | 204.68 | 65.76 | 9.31
 | MP (NVDA) | 263.44 | 5.44 | 8.84 | 9.45 | 5.42 | 0.57 | 29.72 | 11.28 | 61.35
12. | Maharashtra | 516.00 | 16.26 | 20.87 | 33.96 | 33.09 | 13.51 | 117.69 | 22.81 | 185.36
13. | Manipur | 22.04 | 0.00 | 5.03 | 0.00 | 3.63 | 0.00 | 8.66 | 39.30 | 13.38
14. | Odisha | 236.34 | 9.49 | 26.99 | 18.53 | 14.98 | 0.00 | 69.99 | 29.61 | 5.16
15. | Punjab | 142.66 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 49.93
16. | Rajasthan | 117.98 | 8.25 | 7.22 | 7.08 | 5.35 | 2.83 | 30.73 | 26.05 | 32.00
17. | Telangana | 529.03 | 0.00 | 0.00 | 0.00 | 10.68 | 0.00 | 10.68 | 2.02 | 268.36
18. | Uttar Pradesh | 524.38 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 156.67
 | Total | 4505.68 | 509.93 | 450.29 | 394.55 | 110.43 | 22.69 | 1487.88 | 33.02 | 1017.06
7th PIRC Meeting (Virtual, 11th September 2020): Progress Review Presentations
( Area in Th. Ha.)

## Slide 6
MI Progress
Sr. No. | State | CCA Target | CCA Progress | 
 |  |  | Created | % Progress
1. | AP | 0 | 0 | 0.00
2. | Assam | 6.342 | 2.509 | 39.56
3. | Bihar | 3.247 | 0.2 | 6.16
4. | Chhattisgarh | 1.981 | 0 | 0.00
5. | Goa | 1.4 | 0 | 0.00
6 | Gujarat | 0 | 0 | 0.00
7. | J&K | 0.199 | 0.035 | 17.59
8. | Jharkhand | 13.33 | 0 | 0.00
9. | Karnataka | 0 | 0 | 0.00
7th PIRC Meeting (Virtual, 11th September 2020): Progress Review Presentations
( Area in Th. Ha.)

## Slide 7
MI Progress
Sr. No. | State | CCA Target | CCA Progress | 
 |  |  | Created | % Progress
10. | Kerala | 0.526 | 0 | 0.00
11. | Madhya Pradesh (WRD) | 399.343 | 0 | 0.00
 | MP (NVDA) | 0 | 0 | 0.00
12. | Maharashtra | 73.228 | 11.992 | 16.38
13. | Manipur | 2.204 | 0 | 0.00
14. | Odisha | 24.029 | 0.252 | 1.05
15. | Punjab | 14.2658 | 0 | 0.00
16. | Rajasthan | 0 | 0 | 0.00
17. | Telangana | 69.983 | 0 | 0.00
18. | Uttar Pradesh | 0 | 0 | 0.00
 | Total | 610.08 | 14.99 | 2.46
7th PIRC Meeting (Virtual, 11th September 2020): Progress Review Presentations
( Area in Th. Ha.)

## Slide 8
WUA Progress
Sr. No. | State | WUA Target | WUA Progress |  |  |  |  |  |  |  | Infrastructural grant released | Handed over | Target for 2020-21
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress |  |  | 
1. | AP | 418 | 5 | 0 | 0 | 0 | 0 | 46 | 51 | 12 | 0 | 0 | 46
2. | Assam | 100 | 47 | 20 | 5 | 0 | 2 | 0 | 74 | 74 | 0 | 0 | 26
3. | Bihar | 30 | 0 | 0 | 0 | 0 | 10 | 2 | 12 | 40 | 0 | 9 | 16
4. | Chhattisgarh | 32 | 10 | 8 | 0 | 0 | 0 | 0 | 18 | 56 | 0 | 0 | 12
5. | Goa | 110 | 42 | 0 | 0 | 0 | 0 | 0 | 42 | 38 | 42 | 42 | 20
6. | Gujarat | 4466 | 1894 | 428 | 46 | 528 | 414 | 24 | 3334 | 75 | 110 | 1440 | 700
7. | J&K | 6 | 2 | 0 | 0 | 2 | 0 | 0 | 4 | 67 | 0 | 0 | 0
8. | Jharkhand | 256 | 0 | 0 | 0 | 0 | 48 | 0 | 48 | 19 | 0 | 0 | 106
9. | Karnataka | 816 | 48 | 1 | 95 | 77 | 10 | 0 | 231 | 28 | 5 | 57 | 84
(WUA’s in No’s)
7th PIRC Meeting (Virtual, 11th September 2020): Progress Review Presentations

## Slide 9
WUA Progress
Sr. No. | State | WUA Target | WUA Progress |  |  |  |  |  |  |  | Infrastructural grant released | Handed over | Target for 2020-21
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress |  |  | 
10. | Kerala | 240 | 95 | 0 | 0 | 19 | 0 | 0 | 114 | 48 | 0 | 0 | 32
11. | Madhya Pradesh(WRD) | 214 | 174 | 40 | 0 | 0 | 0 | 0 | 214 | 100 | 214 | 214 | 0
 | MP(NVDA) | 160 | 93 | 14 | 1 | 2 | 1 | 0 | 111 | 69 | 0 | 0 | 49
12. | Maharashtra | 1612 | 0 | 291 | 75 | 72 | 192 | 0 | 630 | 39 | 84 | 84 | 624
13. | Manipur | 74 | 0 | 0 | 29 | 5 | 0 | 34 | 68 | 92 | 0 | 0 | 0
14. | Odisha | 545 | 0 | 16 | 69 | 27 | 4 | 0 | 116 | 21 | 74 | 93 | 105
15. | Punjab | 967 | 967 | 0 | 0 | 0 | 0 | 0 | 967 | 100 | 0 | 0 | 0
16. | Rajasthan | 2411 | 2324 | 56 | 1 | 14 | 2 | 12 | 2409 | 100 | 0 | 2185 | 2
17. | Telangana | 1148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
18. | Uttar Pradesh | 1068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | Total | 14673 | 5701 | 874 | 321 | 746 | 683 | 118 | 8443 | 58 | 529 | 4124 | 1854
(WUA’s in No’s)
7th PIRC Meeting (Virtual, 11th September 2020): Progress Review Presentations

## Slide 10
CA Release Progress
Sr. No. | State | Overall CA Target | CA Release Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
1. | AP | 349.37 | 0.00 | 0.00 | 69.18 | 0.00 | 0.00 | 69.18 | 19.80 | 178.62
2. | Assam | 106.27 | 0.00 | 0.00 | 3.56 | 0.00 | 4.00 | 7.56 | 7.11 | 79.26
3. | Bihar | 55.57 | 12.60 | 8.76 | 14.42 | 0.00 | 0.00 | 35.78 | 64.39 | 14.85
4. | Chhattisgarh | 79.57 | 0.00 | 11.80 | 9.93 | 0.00 | 0.00 | 21.73 | 27.31 | 57.86
5. | Goa | 18.78 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 6.78
6 | Gujarat | 2510.88 | 681.64 | 690.48 | 347.04 | 0.00 | 0.00 | 1719.16 | 68.47 | 340.00
7. | J&K | 5.25 | 0.00 | 0.00 | 1.70 | 0.00 | 1.08 | 2.78 | 52.94 | 0.00
8. | Jharkhand | 133.32 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 50.00
9. | Karnataka | 175.88 | 31.42 | 15.25 | 13.49 | 3.79 | 4.45 | 68.40 | 38.89 | 41.08
(CA in Rs. Crores)
7th PIRC Meeting (Virtual, 11th September 2020): Progress Review Presentations

## Slide 11
CA Release Progress
Sr. No. | State | Overall CA Target | CA Release Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
10. | Kerala | 48.71 | 0.00 | 0.00 | 0.00 | 0.00 | 2.69 | 2.69 | 5.52 | 5.00
11. | MP (WRD) | 636.68 | 61.49 | 102.79 | 55.97 | 0.00 | 15.96 | 236.21 | 37.10 | 38.43
 | MP (NVDA) | 605.69 | 16.25 | 0.00 | 14.94 | 0.00 | 0.00 | 31.19 | 5.15 | 20.00
12. | Maharashtra | 1003.70 | 15.17 | 32.81 | 25.79 | 0.00 | 27.36 | 101.13 | 10.08 | 0.00
13. | Manipur | 63.66 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 46.08
14. | Odisha | 420.22 | 35.28 | 58.57 | 3.65 | 0.00 | 22.02 | 119.52 | 28.44 | 
15. | Rajasthan | 228.87 | 0.00 | 0.00 | 0.00 | 0.00 | 18.08 | 18.08 | 7.90 | 0.00
16. | Telangana | 230.05 | 0.00 | 2.48 | 7.44 | 10.22 | 7.02 | 27.16 | 11.81 | 34.38
17. | Uttar Pradesh | 709.49 | 0.00 | 10.22 | 26.12 | 0.00 | 0.00 | 36.34 | 5.12 | 299.53
18. | Punjab | 917.00 | 0.00 | 0.00 | 0.00 | 150.00 | 6.00 | 156.00 | 17.01 | 300.31
 | Total | 8298.96 | 853.86 | 933.15 | 593.23 | 164.01 | 108.66 | 2652.91 | 31.97 | 1512.17
(CA in Rs. Crores)
7th PIRC Meeting (Virtual, 11th September 2020): Progress Review Presentations

## Slide 12
Total Expenditure Progress
Sr. No. | State | Total Expenditure Target | Total Expenditure Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
1. | AP | 971.45 | 0.00 | 0.00 | 0.00 | 0.51 | 0.41 | 0.92 | 0.09 | 0.41
2. | Assam | 215.46 | 0.00 | 8.76 | 13.20 | 9.64 | 8.00 | 39.60 | 18.38 | 161.22
3. | Bihar | 148.57 | 7.86 | 20.17 | 17.55 | 11.53 | 3.24 | 60.35 | 40.62 | 84.04
4. | Chhattisgarh | 159.85 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 159.85
5. | Goa | 153.65 | 4.72 | 7.16 | 9.09 | 14.16 | 1.11 | 36.24 | 23.59 | 40.00
6 | Gujarat | 5021.77 | 1435.91 | 1224.73 | 861.68 | 76.96 | 9.01 | 3608.29 | 71.85 | 740.91
7. | J&K | 11.64 | 0.00 | 0.00 | 3.44 | 2.57 | 0.00 | 6.01 | 51.63 | 2.12
8. | Jharkhand | 747.53 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 65.00
9. | Karnataka | 1013.09 | 38.95 | 41.64 | 40.29 | 22.26 | 0.00 | 143.14 | 14.13 | 0.00
(TE in Rs. Crores)
7th PIRC Meeting (Virtual, 11th September 2020): Progress Review Presentations

## Slide 13
Total Expenditure Progress
Sr. No. | State | Total Expenditure Target | Total Expenditure Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
10. | Kerala | 107.29 | 1.54 | 0.00 | 0.00 | 0.00 | 0.00 | 1.54 | 1.44 | 10.16
11. | MP (WRD) | 1273.83 | 181.75 | 191.62 | 101.03 | 61.90 | 0.00 | 536.30 | 62.23 | 23.32
 | MP (NVDA) | 1183.34 | 16.07 | 19.52 | 19.15 | 15.68 | 0.00 | 70.42 | 5.95 | 36.24
12. | Maharashtra | 2200.89 | 31.80 | 31.15 | 114.74 | 113.77 | 40.31 | 331.75 | 15.07 | 706.43
13. | Manipur | 122.71 | 0.00 | 19.34 | 0.00 | 15.82 | 0.00 | 35.16 | 28.65 | 87.55
14. | Odisha | 1265.24 | 58.76 | 100.77 | 109.37 | 82.55 | 10.51 | 361.96 | 28.61 | 56.00
15. | Punjab | 477.19 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 167.01
16. | Rajasthan | 450.88 | 11.76 | 12.99 | 14.85 | 28.85 | 6.88 | 75.33 | 16.71 | 78.02
17. | Telangana | 1488.24 | 0.00 | 0.00 | 0.00 | 5.22 | 0.00 | 5.22 | 0.35 | 837.04
18. | Uttar Pradesh | 1861.66 | 0.00 | 0.00 | 0.00 | 0.47 | 0.00 | 0.47 | 0.03 | 600.00
 | Total | 18874.27 | 1789.12 | 1677.84 | 1304.39 | 461.88 | 79.47 | 5312.70 | 28.78 | 3855.33
(TE in Rs. Crores)
7th PIRC Meeting (Virtual, 11th September 2020): Progress Review Presentations

## Slide 14
Broad Review
Sr. No. | State | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | AP | 266.11 | 87.49 | 0.00 | 87.49 | 32.88 | 294.90 | 230.30 | 78.09
2. | Assam | 54.12 | 7.50 | 23.40 | 30.90 | 57.09 | 114.29 | 82.06 | 71.80
3. | Bihar | 32.47 | 1.96 | 15.52 | 17.48 | 53.84 | 39.61 | 27.00 | 68.16
4. | Chhattisgarh | 42.63 | 0.00 | 0.00 | 0.00 | 0.00 | 44.63 | 38.85 | 87.04
5. | Goa | 14.52 | 5.85 | 1.05 | 6.90 | 47.53 | 21.06 | 17.15 | 81.47
6 | Gujarat | 1792.00 | 551.80 | 938.61 | 1490.41 | 83.17 | 1792.00 | 1671.61 | 93.28
7. | J&K | 5.50 | 3.04 | 1.69 | 4.73 | 86.07 | 10.69 | 8.12 | 75.96
8. | Jharkhand | 66.65 | 0.00 | 0.00 | 0.00 | 0.00 | 236.85 | 107.33 | 45.32
9. | Karnataka | 176.48 | 90.93 | 34.85 | 125.78 | 71.27 | 147.81 | 134.63 | 91.08
(CCA in Th. ha.)
7th PIRC Meeting (Virtual, 11th September 2020): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 15
Broad Review
Sr. No. | State | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
10. | Kerala | 18.48 | 1.68 | 0.60 | 2.28 | 12.37 | 30.72 | 28.65 | 93.26
11. | MP (WRD) | 398.34 | 88.08 | 204.68 | 292.76 | 73.50 | 501.10 | 495.80 | 98.94
 | MP (NVDA) | 298.89 | 36.84 | 29.72 | 66.56 | 1.93 | 0.00 | 0.00 | 0.00
12. | Maharashtra | 706.14 | 201.46 | 117.69 | 319.16 | 45.20 | 779.96 | 517.87 | 66.40
13. | Manipur | 22.04 | 0.00 | 8.66 | 8.66 | 39.30 | 0.00 | 0.00 | 0.00
14. | Odisha | 238.96 | 1.65 | 69.99 | 71.64 | 29.98 | 331.57 | 188.32 | 56.80
15. | Punjab | 142.66 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00
16. | Rajasthan | 363.98 | 247.00 | 30.73 | 277.73 | 76.30 | 342.51 | 342.51 | 100.00
17. | Telangana | 529.03 | 0.00 | 10.68 | 10.68 | 2.02 | 636.04 | 342.02 | 53.77
18. | Uttar Pradesh | 524.38 | 0.00 | 0.00 | 0.00 | 0.00 | 663.91 | 343.00 | 51.66
 | Total | 5693.35 | 1325.29 | 1487.88 | 2813.17 | 31.78 | 5987.65 | 4575.22 | 76.41
(CCA in Th. ha.)
7th PIRC Meeting (Virtual, 11th September 2020): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 16
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
√ | Delay in Govt/Administrative clearances.
√ | State budget constraints.
√ | Unwillingness of farmers.
√ | Delays in tendering.
√ | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
7th PIRC Meeting (Virtual, 11th September 2020): Progress Review Presentations

## Slide 17
Thank You

## Slide 18
7Th PIRC (Virtual) MEETING on CADWM on 11th SEPT, 2020
Progress of
Water Resources Department,
Madhya Pradesh
Aditya Sharma
CE, NBO, CWC, Bhopal

## Slide 19
PROJECT IMPLEMENTATION REVIEW COMMITTEE FOR CADWM ON DATED 11 SEPT. 2020 M.P. WRD

## Slide 20
MADHYA PRADESH
Chart: 
7th PIRC Meeting (virtual, 11th Sept 2020): Progress Review Presentations
Number of Projects- 10
Projects Availing CA : 10
Project Included - 10
Project Reporting Progress - 10
Progress
Target

## Slide 21
7th PIRC Meeting (virtual, 11th Sept 2020): Progress Review Presentations |  |  |  |  |  |  |  |  |  | 
CCA PROGRESS |  |  |  |  |  |  |  |  |  | 
(Area in Th.Ha.) |  |  |  |  |  |  |  |  |  | 
S.No. | Project | Balance CCA Target | CCA Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 upto 31.08.2020) | Total | % Progress | 
1 | Sindh Phase II | 90.564 | 28.301 | 29.265 | 9.182 | 2.833 | 0 | 69.581 | 77 | 1.085
2 | Ban Sagar | 97.036 | 19.361 | 15.17 | 10.959 | 6.786 | 0.160 | 52.436 | 54 | 2.00
3 | Pench | 28.068 | 5.828 | 5.19 | 3.194 | 4.591 | 0.163 | 18.966 | 68 | 3.219
4 | Mahan | 14.313 | 2.232 | 5.03 | 0 | 1.357 | 0 | 8.619 | 60 | 0.40
5 | Singhpur | 5.84 | 1.888 | 3.234 | 0 | 0 | 0 | 5.122 | 88 | 0
6 | Mahuar | 9.16 | 5.964 | 2.246 | 0 | 0 | 0 | 8.21 | 90 | 0
7 | Sagad | 9.478 | 1.163 | 2.695 | 4.576 | 0.096 | 0 | 8.53 | 90 | 0
8 | Mahi | 28.127 | 1.06 | 6.067 | 4.656 | 3.537 | 0 | 15.32 | 54 | 1.084
9 | Sanjay Sagar (Bah) | 9.673 | 1.038 | 1.357 | 4.469 | 0.399 | 0 | 7.263 | 75 | 1.021
10 | Bariyarpur | 19.003 | 4.99 | 3.385 | 0.599 | 1.597 | 0.064 | 10.635 | 56 | 0.50
 | Total | 311.26 | 71.825 | 73.639 | 37.635 | 21.196 | 0.387 | 204.682 | - | 9.309

## Slide 22
7th PIRC Meeting (virtual, 11th Sept 2020): Progress Review Presentations |  |  |  |  |  |  |  |  |  | 
WUA PROGRESS |  |  |  |  |  |  |  |  |  | 
(WUA's No'S) |  |  |  |  |  |  |  |  |  | 
S. No. | Project | WUA Target | WUA Progress |  |  |  |  |  |  | Remarks
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | Total | % Progress | 
1 | Sindh Phase-II | 49 | 47 | 2 | 0 | 0 | 0 | 49 | 100 | The construction of w/c& f/c and other activity are being executed through elected WUAs and the work have been already transferred to WUA
2 | Ban Sagar | 67 | 48 | 19 | 0 | 0 | 0 | 67 | 100 | 
3 | Pench | 37 | 24 | 13 | 0 | 0 | 0 | 37 | 100 | 
4 | Mahan | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 100 | 
5 | Singhpur | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 100 | 
6 | Mahuar | 7 | 7 | 0 | 0 | 0 | 0 | 7 | 100 | 
7 | Sagad | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 100 | 
8 | Mahi | 12 | 6 | 6 | 0 | 0 | 0 | 12 | 100 | 
9 | Sanjay Sagar (Bah) | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 100 | 
10 | Bariyarpur | 23 | 23 | 0 | 0 | 0 | 0 | 23 | 100 | 
 | Total | 214 | 174 | 40 | 0 | 0 | 0 | 214 | - | -

## Slide 23
7th PIRC Meeting (virtual, 11th Sept 2020): Progress Review Presentations |  |  |  |  |  |  |  |  |  | 
CA RELEASE PROGRESS |  |  |  |  |  |  |  |  |  | 
(CA in Rs. Crores) |  |  |  |  |  |  |  |  |  | 
S. No. | Project | Overall CA Target |  | CA Release Progress |  |  |  |  |  | Total Central Share required for 2020-21
 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | Total | % Progress | 
1 | Sindh Phase II | 180.76 | 5.57 | 17.19 | 43.31 | 14.29 | 4.38 | 84.74 | 47 | 16.15
2 | Ban Sagar | 224.3 | 14.93 | 22.349 | 15.965 | 18.24 | 4.92 | 76.404 | 34 | 8.55
3 | Pench | 51.22 | 1.41 | 5.351 | 8.602 | 5.9 | 2.84 | 24.103 | 47 | 1.43
4 | Mahan | 27.26 | 1.34 | 2.193 | 6.379 | 3.095 | 0 | 13.007 | 48 | 0.07
5 | Singhpur | 10.367 | 0 | 2.05 | 2.205 | 0.66 | 0 | 4.915 | 47 | 1.67
6 | Mahuar | 16.798 | 1.99 | 2.918 | 5.284 | 0.6 | 0.43 | 11.222 | 67 | 1.618
7 | Sagad | 17.68 | 1.99 | 0 | 4.338 | 2.157 | 0.26 | 8.745 | 49 | 3.112
8 | Mahi | 64.28 | 0.9 | 2.34 | 8.717 | 6.05 | 2.57 | 20.577 | 32 | 3.484
9 | Sanjay Sagar (Bah) | 18.09 | 0 | 0 | 4.022 | 0 | 0.56 | 4.582 | 25 | 2.344
10 | Bariyarpur | 25.926 | 0 | 7.139 | 3.966 | 4.99 | 0 | 16.095 | 62 | 0
 | Total | 636.681 | 28.13 | 61.53 | 102.788 | 55.982 | 15.96 | 264.39 | - | 38.428

## Slide 24
7th PIRC Meeting (virtual, 11th Sept 2020): Progress Review Presentations |  |  |  |  |  |  |  |  | 
TOTAL EXPENDITURE PROGRESS |  |  |  |  |  |  |  |  | 
(TE in Rs. Crores) |  |  |  |  |  |  |  |  | 
S.No. | Project | Total Expenditure target | Total Expenditure Progress |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019- 20 | Total | % Progress | 
1 | Sindh Phase II | 361.531 | 70.895 | 76.687 | 26.967 | 11.50 | 186.05 | 51 | 2.72
2 | Ban Sagar | 448.6 | 49.012 | 38.529 | 27.936 | 17.53 | 133.01 | 30 | 5.01
3 | Pench | 102.438 | 14.609 | 13.723 | 9.067 | 12.15 | 49.549 | 48 | 8.06
4 | Mahan | 54.52 | 5.59 | 12.6 | 0.11 | 3.40 | 21.7 | 40 | 1.00
5 | Singhpur | 21.39 | 4.73 | 8.1 | 0 | 0.00 | 12.83 | 60 | 0
6 | Mahuar | 33.596 | 16.06 | 7.183 | 1.06 | 1.04 | 25.343 | 75 | 0
7 | Sagad | 35.374 | 2.92 | 7.034 | 11.771 | 1.29 | 23.015 | 65 | 0
8 | Mahi | 128.338 | 2.656 | 15.787 | 11.393 | 9.71 | 39.546 | 31 | 2.71
9 | Sanjay Sagar (Bah) | 36.19 | 2.605 | 3.4 | 11.196 | 1.00 | 18.201 | 50 | 2.56
10 | Bariyarpur | 51.851 | 12.675 | 8.573 | 1.533 | 4.28 | 27.061 | 52 | 1.26
 | Total | 1273.83 | 181.752 | 191.616 | 101.033 | 61.90 | 536.301 | - | 23.32

## Slide 25
7th PIRC Meeting (virtual, 11th Sept 2020): Progress Review Presentations |  |  |  |  |  |  |  |  | 
BROAD PROGRESS |  |  |  |  |  |  |  |  | 
(CCA in Th. Ha.) |  |  |  |  |  |  |  |  | 
S No | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA Developed before 31.03.16 (A)* | Progress in CCA for 99 priority projects (B) | Cumulative CCA developed (A+B) | % CCA progress | Ultimate irrigation potential | Potential created | % IPC
1 | Sindh Phase II | 98.25 | 7.686 | 69.581 | 75.733 | 77 | 162.1 | 162.1 | 100
2 | Ban Sagar | 154.687 | 57.651 | 52.276 | 108.77 | 70 | 154.54 | 154.54 | 100
3 | Pench | 28.268 | 0.2 | 18.803 | 18.863 | 67 | 28.268 | 25.27 | 89
4 | Mahan | 16.15 | 1.837 | 8.619 | 10.456 | 65 | 19.74 | 19.74 | 100
5 | Singhpur | 6 | 0.16 | 5.122 | 5.282 | 88 | 10.2 | 10.2 | 100
6 | Mahuar | 9.5 | 0.34 | 8.21 | 8.55 | 90 | 13.78 | 13.78 | 100
7 | Sagad | 9.478 | 0 | 8.53 | 8.53 | 90 | 17.06 | 17.06 | 100
8 | Mahi | 28.127 | 0 | 15.32 | 14.617 | 52 | 33.75 | 33.1 | 98
9 | Sanjay Sagar (Bah) | 9.893 | 0.22 | 7.263 | 7.084 | 72 | 17.81 | 17.81 | 100
10 | Bariyarpur | 38.99 | 19.987 | 10.571 | 30.558 | 78 | 43.85 | 43.85 | 100
 | Total | 399.343 | 88.081 | 204.295 | 288.443 | 73 | 501.1 | 495.8 | 99

## Slide 26
PROPOSED MICRO IRRIGATION FOR CADWM PROJECT |  |  |  |  | 
S.No. | Name of Project | Project CCA | Sanction received from GoI MoWR for Micro Irrigation Area |  | Remarks
 |  |  | Area (in Th. Ha.) | Amount (in crore) | 
1 | Sagad Project | 9.478 | 0.971 | 4.812 | N 19011/35/2017/CADWM Dt. 03.07.17
2 | Sanjay Sagar (Bah) | 9.893 | 0.989 | 4.945 | N 19011/35/2017CADWM Dt. 03.07.17
3 | Pench Diversion | 28.268 | 7.123 | 35.61 | N 19011/35/2017/CADWM Dt. 04.09.17
4 | Mahan | 16.15 | 1.615 | 8.075 | N 19011/35/2017 CADWM Dt. 04.09.17
5 | Singhpur | 6 | 0.6 | 3 | N 04/27/07/2017/Punasa/22427 Dt. 02.05.18
6 | Bansagar | 154.687 | 15.5 | 77.5 | CWC No. - 04/15/2015 (P&A)/ 124-28 Dt 03.05.18
7 | Sindh Phase-II | 98.25 | 9.988 | 49.94 | 04/12/2015 (P&A) / Sindh/313-16/Dt. 08.11.18
8 | Mahuar Medium | 9.5 | 1.033 | 5.164 | N -4/35/2015/iz- ,oa- iq&05&07 Dt. 08.01.2020
9 | Mahi | 28.127 | 11.723 | 0 | The project includes micro irrigation for 9900 ha. therefore separate micro irrigation proposal is not prepared.
10 | Bariyarpur | 38.99 | 0 | 0 | The project has been included in the year 2011-12 therefore micro irrigation activity is not proposed.
 | Total for WRD | 399.343 | 49.542 | 189.046 | 

## Slide 27
WORK PLAN FOR MICRO IRRIGATION |  |  |  |  |  |  | 
S.No. | Name of project | CCA Proposed under CADWM | Area proposed for Micro Irrigation | Physical progress upto 31.03.20 | Balance work as on 01.04.20 | Work plan of micro irrigation | 
 |  |  |  |  |  | 2020-21 | 2021-22
1 | Sindh Phase-II | 98.25 | 9.988 | - | 9.988 | 4.994 | 4.994
2 | Bansagar | 154.687 | 15.500 | - | 15.500 | 7.75 | 7.75
3 | Pench Diversion | 28.268 | 2.8 | - | 2.8 | 1.4 | 1.4
4 | Mahan | 16.15 | 1.615 | - | 1.615 | 0.807 | 0.808
5 | Singhpur | 6 | 0.600 | - | 0.600 | 0.3 | 0.3
6 | Mahuar Medium | 9.5 | 1.033 | - | 1.033 | 0.516 | 0.517
7 | Sagad | 9.478 | 0.971 | - | 0.971 | 0.485 | 0.486
8 | Mahi | 28.127 | 11.723 | - | 11.723 | 5.861 | 5.862
9 | Sanjay Sagar (Bah) | 9.893 | 0.989 | - | 0.989 | 0.495 | 0.494
10 | Bariyarpur | 38.99 | 0.000 | - | 0.000 | - | -
 | Total | 441.993 | 49.542 |  | 49.542 | 24.769 | 24.773

## Slide 28
Command Area Developmental works executed in MPWRD |  |  |  |  |  |  |  |  | 
S.No. | Project | Estimated Cost | CCA | Activities of Command Area Development Works |  |  |  |  | 
 |  |  |  | Survey | Water Course /Field Channel | One Time Functional Grand to WUA | Training | Micro Irrigation | Remaining Activities
1 | Sindh Phase II | 394.090 | 98.250 | This Activity is being executed through WUA | The construction work Water Course and Field channel is being executed by WUA with the help of Competent Authority | This Activity is being conducted as per provisions of CADWM guidelines with the help of farmers and WUA authorities | The Training is imparted to WUA members, Farmers and officers of the department in field and WALMI, Bhopal | The Micro Irrigation Projects have been Sanctioned NBO,CWC, Bhopal. This Activities is proposed to be conducted by tendering process. | As per CADWM Program activities like construction of field drain, field leveling, CSD, reclamation of Water logging etc is not required as per field requirement
2 | Ban Sagar | 591.463 | 154.687 |  |  |  |  |  | 
3 | Pench | 102.438 | 28.268 |  |  |  |  |  | 
4 | Mahan | 60.560 | 16.150 |  |  |  |  |  | 
5 | Singhpur | 22.550 | 6.000 |  |  |  |  |  | 
6 | Mahuar | 35.670 | 9.500 |  |  |  |  |  | 
7 | Sagad | 35.510 | 9.478 |  |  |  |  |  | 
8 | Mahi | 128.730 | 28.127 |  |  |  |  |  | 
9 | Sanjay Sagar (Bah) | 37.050 | 9.893 |  |  |  |  |  | 
10 | Bariyarpur | 85.416 | 38.990 |  |  |  |  |  | 
 | Total | 1493.477 | 399.343 |  |  |  |  |  | 

## Slide 29
PENCH PROJECT

## Slide 30
PENCH PROJECT

## Slide 31
PENCH PROJECT
BANSAGAR PROJECT

## Slide 32
BANSAGAR PROJECT

## Slide 33
THANKS

## Slide 34
7TH PROJECT IMPLEMENTATION REVIEW COMMITTEE MEETING
(Virtual Platform)
For CADWM Projects
Of
Narmada Valley Development Authority, GoMP
on
11th Sep. 2020
Aditya Sharma
Chief Engineer
NBO, CWC, Bhopal (M.P.)

## Slide 35
7th PIRC Meeting ( Virtual Platform) 11th September 2020: Progress Review Presentations

## Slide 36
N
ORISSA
ANDHRA
PRADESH
MAHARASHTRA
BIHAR
UTTAR PRADESH
JAGDALPUR
RAIPUR
RAIGARH
MAHANADI BASIN
GODAVARI BASIN
AMBIKAPUR
URMIL
Ken
Urmil
Mahanadi
MANDLA
Indravati
Yamuna
Ganga
Sone
BANSAGAR
GWALIOR
Sindh
Chambal
MAHI
Chambal
Dhasan
Wainganga
Hasdeo
Shivnath
BILASPUR
HARSI DAM
KAKETO
Parbati
Tons
Kahnar
Sabari
Rehar
Mand
Purna
Kotri
Banas
Godavari
Kunwari
Jamni
Pahuj
GANGA BASIN
Map not to scale
For State boundaries refer to Survey of India maps
INDRAVATI(SUB)BASIN
Baghain
Pench
Bagh
Ib
Johilla
88M
REWA
Gopad
MANIKHEDA
DATIA
SIDHI
KUNWARI LIFT
53M
SONE(SUB)BASIN
SUTIAPAT
BRAHAMANI
BAITARNI BASIN
WAINGANGA(SUB)BASIN
GUJARAT
DHAR
UJJAIN
NARMADA BASIN
Kali Sindh
Narmada
JHABUA
Mahi
Tapi
Parbati
TAPI BASIN
MAHI BASIN
Anas
RATLAM
RAJASHTAN
BHOPAL
JABALPUR
INDORE
BARGI
SAGAR
YAMUNA(SUB)BASIN
SEONI
Betwa
CHHINDWARA
INDIRA SAGAR
BETUL
HOSHANGABAD
M.P.
CHHATISGARH
Projects under NVDA, Govt. of Madhya Pradesh
LOCATION MAP –-CADWM PROJECTS
CHHATARPUR
BARIARPUR
WEIR
OMKARESHWAR PROJECT
INDIRA SAGAR PROJECT
BARGI DIVERSION PROJECT
OSP (PHASE-I)
OSP (PHASE-II)
OSP (PHASE-III)
OSP (PHASE-IV)
ISP (PHASE- I & II)
ISP (PHASE-III)
ISP (PHASE-IV)
ISP (PHASE-V)
BDP (PHASE- I)
BDP (PHASE-II)
7th PIRC Meeting ( Virtual Platform) 11th September 2020: Progress Review Presentations

## Slide 37
NVDA, MADHYA PRADESH
7th PIRC Meeting ( Virtual Platform) 11th September 2020: Progress Review Presentations
Number of Projects: 12 NVDA
Projects Availing CA : 10 NVDA
Project Included - 10
Project Reporting Progress - 10
Progress
Chart: 

## Slide 38
CCA PROGRESS |  |  |  |  |  |  |  |  |  |  | 
(Area in Th.Ha.) |  |  |  |  |  |  |  |  |  |  | 
S. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
1 | BDP Phase –I | 21.194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.000
2 | BDP Phase –II | 31.90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.845
 | Total BDP | 53.093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.845
3 | ISP Canal Phase I & II | 14.56 | 4.783 | 1.244 | 1.799 | 1.397 | 0 | 0 | 9.223 | 63 | 1.00
4 | ISP Canal Phase III | 20.70 | 0.905 | 0.397 | 0.480 | 0.409 | 0 | 0 | 2.191 | 11 | 0.5
5 | ISP Canal Phase IV | 19.60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ISP Canal Phase -V | 33.14 | 0 | 0.733 | 0.235 | 0 | 0 | 0 | 0.968 | 3 | 0
 | Total ISP | 88.00 | 5.688 | 2.374 | 2.514 | 1.806 | 0.00 | 0.00 | 12.382 | 14 | 1.500
7 | OSP Canal Phase –I | 21.00 | 0.919 | 2.378 | 2.23 | 1.432 | 1.433 | 0 | 8.295 | 40 | 2.000
8 | OSP Canal Phase –II | 19.128 | 3.212 | 3.065 | 2.458 | 0.705 | 1.365 | 0 | 10.805 | 56 | 2.000
9 | OSP Canal Phase –III | 48.592 | 0 | 0 | 3.865 | 6.936 | 2.984 | 0 | 13.785 | 28 | 15.000
10 | OSP Canal Phase –IV | 54.63 | 0 | 0 | 0 | 0 | 1.075 | 0.570 | 1.132 | 2 | 10.000
 | Total OSP | 143.350 | 4.131 | 5.443 | 8.556 | 9.073 | 6.857 | 0.57 | 34.117 | 24 | 29.00
 | Grand Total | 284.443 | 9.819 | 7.817 | 11.07 | 10.879 | 6.857 | 0.57 | 46.499 | 16.43 | 36.00
7th PIRC Meeting ( Virtual Platform) 11th September 2020: Progress Review Presentations

## Slide 39
WUA PROGRESS |  |  |  |  |  |  |  |  |  |  | 
(WUA's No'S) |  |  |  |  |  |  |  |  |  |  | 
S.No. | Project | WUA Target | WUA Progress |  |  |  |  |  |  |  | Target for 2020-21
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
1 | BDP Phase –I | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 100 | 0
2 | BDP Phase –II | 15 | 13 | 0 | 1 | 0 | 1 | 0 | 15 | 100 | 0
 | Total BDP | 27 | 27 | 0 | 1 | 0 | 0 | 0 | 27 | 100 | 0
3 | ISP Canal Phase I & II | 25 | 23 | 0 | 0 | 2 | 0 | 0 | 25 | 100 | 0
4 | ISP Canal Phase III | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 26 | 11
5 | ISP Canal Phase IV | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
6 | ISP Canal Phase -V | 18 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 27 | 13
 | Total ISP | 66 | 30 | 0 | 0 | 0 | 0 | 0 | 32 | 48 | 34
7 | OSP Canal Phase –I | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 100 | 0
8 | OSP Canal Phase –II | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 100 | 0
9 | OSP Canal Phase –III | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 28 | 100 | 0
10 | OSP Canal Phase –IV | 29 | 0 | 14 | 0 | 0 | 0 | 0 | 14 | 48 | 15
 | Total OSP | 81 | 52 | 14 | 0 | 0 | 0 | 0 | 66 | 82 | 15
 | Grand Total | 174 |  |  |  |  |  |  | 125 | 72 | 49
7th PIRC Meeting ( Virtual Platform) 11th September 2020: Progress Review Presentations

## Slide 40
CA RELEASE PROGRESS |  |  |  |  |  |  |  |  |  |  | 
(CA in Rs. Crores) |  |  |  |  |  |  |  |  |  |  | 
S.No. | Project | Overall CA Target | CA Release Progress |  |  |  |  |  |  |  | 
 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | Total Central Share required for 2020-21 (Including previous pending demand)
1 | BDP Phase –I | 41.184 | 0 | 0 | 0 | 5.98 | 0 | 0 | 5.98 | 14.52 | 3.0
2 | BDP Phase –II | 60.868 | 0 | 0 | 0 | 8.96 | 0 | 0 | 8.96 | 14.72 | 3.0
 | Total BDP | 102.05 | 0 | 0 | 0 | 14.94 | 0 | 0 | 14.94 | 14.63 | 
3 to 6 | ISP Canal Project (overall Phase (I& II), III, (IV, V) | 196.72 | 9.33 | 6.644 | 0 | 0 | 0 | 0 | 15.97 | 8.12 | 4.0
7 to 10 | OSP Canal Project (overall Phase I, II, III & IV) | 306.92 | 16.650 | 9.610 | 0 | 0 | 0 | 0 | 26.26 | 8.56 | 10.0
 | Total | 605.692 | 25.98 | 16.257 | 0 | 14.94 |  |  | 57.17 | 9.44 | 20
7th PIRC Meeting ( Virtual Platform) 11th September 2020: Progress Review Presentations

## Slide 41
TOTAL EXPENDITURE PROGRESS |  |  |  |  |  |  |  |  |  |  | 
(TE in Rs. Crores) |  |  |  |  |  |  |  |  |  |  | 
S.No. | Project | Total Expenditure target |  | Total Expenditure Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
1 | BDP Phase –I | 82.45 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0.85 | 1 | 1.8
2 | BDP Phase –II | 121.987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.14
 | Total BDP | 204.44 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0.85 | 0.4 | 3.94
3 | ISP Canal Phase I & II | 61.80 | 10.01 | 3.29 | 3.57 | 3.26 | 0.12 | 0.00 | 20.25 | 32.77 | 5.2
4 | ISP Canal Phase III | 87.87 | 1.56 | 0.89 | 1.20 | 1.03 | 0.00 | 0.00 | 4.67 | 5.31 | 1.3
5 | ISP Canal Phase IV | 83.20 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | -
6 | ISP Canal Phase -V | 179.95 | 0.00 | 2.51 | 1.87 | 0.02 | 0.83 | 0.00 | 5.23 | 2.90 | -
 | Total ISP | 412.82 | 11.57 | 6.69 | 6.64 | 4.30 | 0.95 | 0.00 | 30.15 | 7.3 | 6.5
7 | OSP Canal Phase –I | 79.652 | 3.02 | 3.99 | 3.52 | 2.51 | 2.29 | 0.00 | 15.33 | 18.33 | 3.0
8 | OSP Canal Phase –II | 67.020 | 3.72 | 4.63 | 3.71 | 1.70 | 2.05 | 0.00 | 15.80 | 23.15 | 3.0
9 | OSP Canal Phase –III | 169.57 | 0.00 | 0.00 | 9.17 | 13.14 | 11.83 | 0.00 | 34.14 | 20.13 | 15.2
10 | OSP Canal Phase –IV | 326.63 | 0.00 | 4.75 | 0.00 | 0.00 | 0.00 | 0.00 | 4.75 | 1.45 | 7.6
 | Total OSP | 642.87 | 6.74 | 13.37 | 16.40 | 17.35 | 16.17 | 0.00 | 70.03 | 10.89 | 28.8
 | Grand Total | 1260.13 | 18.31 | 20.06 | 23.04 | 21.65 | 17.97 | 0.00 | 101.03 | 8.00 | 39.24
7th PIRC Meeting ( Virtual Platform) 11th September 2020: Progress Review Presentations

## Slide 42
BROAD PROGRESS |  |  |  |  |  |  |  |  |  |  | 
(CCA in Th. Ha., Expenditure in Cr) |  |  |  |  |  |  |  |  |  |  | 
S No | Project | CADWM- Physical |  |  |  |  | CADWM- Financial |  |  |  | 
 |  | Total CCA of Project | CCA Developed before 31.03.15 (A) | Progress in CCA for 99 priority projects (B) | Cumulative CCA developed (A+B) | % CCA progress | Estimated cost of project | Expenditure Before 31.03.2015 (C) | Progress in expenditure for 99 priority projects (D) | Cumulative Expenditure (C+D) | % Expenditure progress
1 | BDP Phase –I | 22.587 | 1.393 | 0 | 1.393 | 6.167 | 85.13 | 2.68 | 0.85 | 3.53 | 4
2 | BDP Phase –II | 31.90 | 0 | 0 | 0 | 0 | 121.99 | 0 | 0 | 0 | 0
 | Total BDP | 54.487 | 1.393 | 0 | 1.393 | 0 | 207.11 | 2.68 | 0.85 | 3.53 | 1.7
3 | ISP Phase I & II | 49.560 | 35.000 | 9.223 | 44.223 | 89 | 113.33 | 51.53 | 20.25 | 71.78 | 63.3
4 | ISP Phase III | 20.700 | 0 | 2.191 | 2.191 | 11 | 87.87 | 0 | 4.67 | 4.67 | 5.31
5 | ISP Phase IV | 19.600 | 0 | 0 | 0 | 0 | 83.20 | 0 | 0 | 0 | 0
6 | ISP Phase -V | 33.140 | 0 | 0.968 | 0.968 | 3 | 179.95 | 0 | 5.23 | 5.23 | 2.9
 | Total ISP | 123.000 | 35.000 | 12.382 | 47.382 | 38.5 | 464.35 | 51.53 | 30.15 | 81.68 | 18
7 | OSP Canal Phase –I | 24.000 | 3.000 | 8.295 | 11.395 | 47 | 83.65 | 3.998 | 15.33 | 19.33 | 23.1
8 | OSP Canal Phase –II | 19.578 | 0.450 | 10.805 | 11.255 | 57 | 68.24 | 1.22 | 15.81 | 17.030 | 25.0
9 | OSP Canal Phase –III | 48.592 | 0 | 13.785 | 13.785 | 28 | 169.57 | 0 | 34.14 | 34.140 | 20.1
10 | OSP Canal Phase –IV | 54.630 | 0 | 1.132 | 1.132 | 2 | 326.63 | 0 | 4.750 | 4.750 | 1.4
 | Total OSP | 146.800 | 3.450 | 34.117 | 37.467 | 26 | 648.08 | 5.22 | 70.03 | 75.25 | 11.61
 | Grand Total | 324.287 | 39.843 | 46.499 | 86.342 | 27 | 1319.54 | 59.43 | 101.03 | 160.46 | 12
7th PIRC Meeting ( Virtual Platform) 11th September 2020: Progress Review Presentations

## Slide 43
ISP-I&II: BORGAON DISTRIBUTARY OUTLET NO 3
ISP-III: JUNAPANI DISTRIBUTARY
ISP-V: OUTLET NO 193
OSP-II: Water-course at Direct Minor # 30
PHOTOGRAPHS

## Slide 44
0SP-III: DISTRIBUTARY NO # 9
OSP IV: Bagarda Minor PFCMD Box
OSP-II: Water-course at Direct Minor # 15
PHOTOGRAPHS
OSP-II: Water-course at Direct Minor # 20

## Slide 45
THANKS

## Slide 46
7Th PIRC (VIRTUAL) MEETING on CADWM on 11th SEPT, 2020
Progress of
Water Resources Department,
Chhattisgarh
Aditya Sharma
CE, NBO, CWC, Bhopal

## Slide 47
Chattisgarh
Number of Projects : 3 Projects Included: 3 Projects Availing CA: 3 Projects Reporting Progress:0
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | Balance CCA (in th. Ha.) | WUA (Nos)
Target | 159.764 | 79.569 | 42.625 | 127
Progress | 0 | 21.71 | 0 | 0
Physical Progress
7th PIRC Meeting (on 11th Sept. 2020): Progress Review Presentations

## Slide 48
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | Total | % Progress | 
1 | Kharung Tank | 8.300 | 0 | 0 | 0 | 0 | 0 | 0 | 8.300
2 | Maniyari Tank | 11.515 | 0 | 0 | 0 | 0 | 0 | 0 | 11.515
3 | Kelo Project | 22.810 | 0 | 0 | 0 | 0 | 0 | 0 | 22.810
 | TOTAL | 42.625 | 0 | 0 | 0 | 0 | 0 | 0 | 42.625
( Area in Th. Ha.)
7th PIRC Meeting (on 11th Sept. 2020): Progress Review Presentations

## Slide 49
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | Total | % Progress | 
1 | Kharung Tank | 10 | 10 | 0 | 0 | 0 | 0 | 10 | 100% | 0
2 | Maniyari Tank | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 100% | 0
3 | Kelo Project | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
 | TOTAL | 30 | 10 | 8 | 0 | 0 | 0 | 18 | 100% | 12
(WUA’s in No’s)
7th PIRC Meeting (on 11th Sept. 2020): Progress Review Presentations

## Slide 50
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | Total | % Progress | 
1 | Kharung Tank | 16.426 | 0 | 0 | 4.95 | 0 | 4.95 | 30.14 | 11.476
2 | Maniyari Tank | 22.629 | 0 | 0 | 4.98 | 0 | 4.98 | 22.01 | 17.649
3 | Kelo Project | 40.515 | 0 | 11.78 | 0 | 0 | 11.78 | 29.08 | 28.735
 | TOTAL | 79.57 | 0 | 11.78 | 9.93 | 0 | 21.71 | 27.07 | 57.86
(CA in Rs. Crores)
7th PIRC Meeting (on 11th Sept. 2020): Progress Review Presentations

## Slide 51
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | Total | % Progress | 
1 | Kharung Tank | 33.1828 | 0 | 0 | 0 | 0 | 0 | 0 | 33.1828
2 | Maniyari Tank | 45.3722 | 0 | 0 | 0 | 0 | 0 | 0 | 45.3722
3 | Kelo Project | 81.2989 | 0 | 0 | 0 | 0 | 0 | 0 | 81.2989
 | TOTAL | 159.8 | 0 | 0 | 0 | 0 | 0 | 0 | 159.8539
(TE in Rs. Crores)
7th PIRC Meeting (on 11th Sept. 2020): Progress Review Presentations

## Slide 52
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Kharung Tank | 8.300 | 0 | 0 | 0 | 0 | 10.30 | 10.30 | 100
2 | Maniyari Tank | 11.515 | 0 | 0 | 0 | 0 | 11.52 | 11.52 | 100
3 | Kelo Project | 22.81 | 0 | 0 | 0 | 0 | 22.81 | 17.005 | 74.55
 | TOTAL | 42.625 | 0 | 0 | 0 | 0 | 44.63 | 38.845 | 
(CCA in Th. ha.)
7th PIRC Meeting (on 11th Sept. 2020): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 53
Key Reasons For Progress Delays
 | Key Reason
X | Absence of Hydraulic Connectivity up to Outlet.
X | Delay in Govt/Administrative clearances.
X | State budget constraints.
X | Unwillingness of farmers.
√ | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
√ | Other Issue – The main season for delay in progress of work is due to delay in finalization of tender, because of either higher rates quoted by tenderer or non qualifying of tenderers.
7th PIRC Meeting (on 11th Sept. 2020): Progress Review Presentations

## Slide 54
7th PIRC Meeting (on 11th Sept. 2020): Progress Review Presentations
CHHATTISGARH
Extra Slides
  Tender for CADWM works of Kharung project has been finalized in three groups. For first group work order has been issued and survey works has been started by agency. For remaining two groups, tendering is done and the rates quoted by agency has to be accepted by Govt, which is expected to be done within a week time.
  Tender for CADWM works of Maniyari project has been finalized in four groups. For two group, work order has been issued and works yet to be started. For remaining two groups, tendering is done and the rates quoted by agency has to be accepted by Govt, which is expected to be done within a week time.
  (ii) The expected completion of CADWM work of Kharung and Maniyari Projects is proposed as 30th June 2021.

## Slide 55
THANKS………
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 56: Monitoring Central Organisation Nagpur, Maharashtra
7th Meeting of
Project Implementation Review Committee (PIRC)
for CADWM Implementation under 99 Prioritized Projects
(MAHARASHTRA)
11th September 2020

## Slide 57
Projects Included in CADWM Programme
(1) Arjuna | (9) Krishna Koyana LIS | (17) Sangola Branch Canal
(2) Aruna | (10) Kudali | (18) Tarali
(3) Bawanthadi (IS) | (11) Lower Dudhna | (19) Tillari
(4) Bembla | (12) Lower Panzara | (20) Upper Kundalika
(5) Dhom Balakwadi | (13) Lower Pedhi | (21) Upper Pen Ganga
(6) Gadnadi | (14) Lower Wardha | (22) Waghur
(7) Gosikhurd (NP) | (15) Morna (Gureghar) | 
(8) Khadakpurna | (16) Nandur Madhmeshwar Ph-II | 
Number of Projects : 22 Projects Included: 22 Projects Availing CA: 18 Projects Reporting Progress:14

## Slide 58
M A D H Y A P R A D E S H
M A H A R A S H T R A
A N D H R A P R A D E S H
K A R N A T A K A
A
R
A
B
I
A
N
S
E
A
NAGPUR
BHANDARA
WARDHA
CHANDRAPUR
GARHCHIROLI
AKOLA
LATUR
BEED
AMRAVATI
YAVATMAL
BULDANA
PARBHANI
OSMANABAD
PUNE
SATARA
SANGLI
KOLHAPUR
RATNAGIRI
DHULE
JALGAON
NASIK
THANE
MUMBAI
Tapi
Girna
Dudhna
Wainganga
Tapi
Wan
Wardha
unavati
Ar
Penganga
Godavari
Godavari
Manar
Manjra
Terna
Sina
Bhima
Krishna
Mula
730
740
750
760
770
780
790
800
810
790
800
810
780
770
760
750
740
730
170
180
190
200
210
210
200
190
180
170
160
160
PROJECTS OF MAHARASHTRA BEING MONITORED BY
MONITORING CENTRAL ORGANISATION
CENTRAL WATER COMMISSION, NAGPUR
(PMKSY-CADWM PROJECTS)
District HQs
Ongoing Major Project
Ongoing Medium Project
Gosikhurd
Waghur
0
60
120
180
240
360Km
SCALE
AURANGABAD
SOLAPUR
JALNA
NANDED
WASHIM
RAIGARH
SINDHUDURG
AHMADNAGAR
Upper Penganga
60
Lower Dudhna
Bawanthadi
Tillari
GOA
Lower Wardha
Khadakpurna
Bembla
Arjuna
Tarali
Morna(G)
Sangola Br.Canal
Gadnadi
Aruna
Dhom Balakwadi
Krishna Koyna LIS
Lower Panzara
Upper Kundlika
Lower Pedhi
Kudali
Nandur Madhameswar
LOCATION MAP

## Slide 59
MAHARASHTRA
7th PIRC Meeting : Progress Review Presentations
Chart: 
| Expenditure (Rs in Crore) | CA (Rs in Crore) | Balance CCA (Th. Ha) | WUAs (Nos)
Target | 2200.89 | 1003.7 | 516 | 1612
Progress upto July-20 | 331.752 | 107.76 | 117.694 | 923
WUAs registered upto July-20 | 525
Physical Progress
(15.07%)

## Slide 60
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  |  |  | Target for 2020-21 | Target date of Completion
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (upto 07/20) | Total | % Progress |  | 
1. | Arjuna | 5.704 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 2.787 | Mar-22
2. | Aruna | 5.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 1.735 | Mar-23
3. | Bawanthadi (IS) | 2.5 | 0 | 0.30 | 0.62 | 0.35 | 0.36 | 1.63 | 65.20 | 1.210 | Jun-21
4. | Bembla | 29.78 | 0 | 2.306 | 3.817 | 1.812 | 3.207 | 11.142 | 37.41 | 4.000 | Mar-23
5. | Dhom Balakwadi | 18.10 | 11.806 | 1.2 | 1.456 | 1.029 | 0.125 | 15.616 | 86.28 | 2.608 | Mar-21
6. | Gadnadi | 3.111 | 0 | 0 | 0 | 0 | 0.025 | 0.025 | 0.80 | 3.111 | Mar-21
7. | Gosikhurd (NP) | 176.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 35.553 | Mar-24
8. | Khadakpurna | 15.72 | 1.937 | 0.485 | 0.796 | 3.413 | 0.06 | 6.691 | 42.56 | 9.089 | Mar-22
9. | Krishna Koyana LIS | 52.82 | 0 | 0 | 1.62 | 2.002 | 2.172 | 5.794 | 10.97 | 49.202 | Jun-21
10. | Kudali | 5.327 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 2.8770 | Mar-22
11. | Lower Dudhna | 30.04 | 0 | 0 | 6.127 | 4.688 | 3.456 | 14.271 | 47.51 | 15.40 | Mar-22
(Area in Th. Ha.)
7th PIRC Meeting : Progress Review Presentations

## Slide 61
CCA Progress-Contd..
( Area in Th. Ha.)
7th PIRC Meeting : Progress Review Presentations
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  |  |  | Target for 2020-21 | Target date of Completion
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (upto 07/20) | Total | % Progress |  | 
12 | Lower Panzara | 6.785 | 0 | 0 | 1.297 | 4.913 | 0.05 | 6.26 | 92.26 | 0.574 | Sep-20
13 | Lower Pedhi | 10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 2.660 | Mar-23
14 | Lower Wardha | 62.45 | 2.516 | 14.272 | 8.192 | 3.774 | 0.24 | 28.994 | 46.43 | 12.00 | Mar-23
15 | Morna (Gureghar) | 4.229 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 1.00 | Mar-23
16 | Nandur Madhmeshwar Ph-II | 23.12 | 0 | 0.790 | 0.432 | 0.625 | 0.11 | 1.957 | 8.46 | 9.800 | Mar-22
17 | Sangola Branch Canal | 6.883 | 0 | 0 | 0.149 | 0 | 0 | 0.149 | 2.16 | 3.367 | Mar-22
18 | Tarali | 13.09 | 0 | 0 | 0 | 4.079 | 1.5 | 5.579 | 42.62 | 5.042 | Mar-21
19 | Tillari | 6.68 | 0 | 0 | 0 | 0 | 0.617 | 0.617 | 9.24 | 2.100 | Jun-21
20 | Upper Kundalika | 2.8 | 0 | 0 | 2.3 | 0.25 | 0 | 2.55 | 91.07 | 1.250 | Dec-20
21 | Upper Pen Ganga | 17.29 | 0 | 1.093 | 1.327 | 1.988 | 1.037 | 5.445 | 31.49 | 4.737 | Mar-23
22 | Waghur | 17.97 | 0 | 0.423 | 5.825 | 4.171 | 0.555 | 10.974 | 61.07 | 7.553 | Dec-20
 | Total | 515.999 | 16.259 | 20.869 | 33.958 | 33.094 | 13.514 | 117.694 | 22.81 | 177.655 | 

## Slide 62
WUA Progress
Sr. No. | Project | WUA Target | WUA formed (upto 07/20) | WUA Progress (Registered with division) |  |  |  |  |  |  |  | Target for 2020-21 | Release of grant (Rs. In Cr.) | Handing over of Assets
 |  |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (upto 07/20) | Total | % Progress |  |  | 
1 | Arjuna | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 3 | 0 | 0
2. | Aruna | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 10 | 0 | 0
3. | Bawanthadi (IS) | 60 | 55 | 0 | 0 | 42 | 0 | 13 | 0 | 55 | 91.67 | 5 | 0.215 | 8
4. | Bembla | 175 | 142 | 0 | 105 | 0 | 20 | 122 | 0 | 142 | 81.14 | 20 | 0 | 1
5. | Dhom Balakwadi | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 35 | 0.45 | 0
6. | Gadnadi | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 7 | 0 | 0
7. | Gosikhurd (NP) | 387 | 166 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.00 | 15 | 0 | 0
8. | Khadakpurna | 63 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 47 | 0.103 | 0
9. | Krishna Koyana LIS | 237 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 241 | 0.28 | 0
10. | Kudali | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 7 | 0 | 0
11. | Lower Dudhna | 72 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 17 | 0 | 0
(WUA’s in Nos)
7th PIRC Meeting : Progress Review Presentations
WUA Progress

## Slide 63
WUA Progress-Contd..
Sr. No. | Project | WUA Target | WUA formed (upto 07/20) | WUA Progress (Registered with division) |  |  |  |  |  |  |  | Target for 2020-21 | Release of grant (Rs. In Cr.) | Handing over of Assets
 |  |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (upto 07/20) | Total | % Progress |  |  | 
12. | Lower Panzara | 15 | 15 | 0 | 0 | 0 | 15 | 0 | 0 | 15 | 100.00 | 15 | 0 | 0
13. | Lower Pedhi | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 0 | 0 | 0
14. | Lower Wardha | 138 | 123 | 0 | 71 | 27 | 12 | 1 | 0 | 111 | 80.43 | 30 | 0 | 26
15. | Morna (Gureghar) | 18 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 5.56 | 10 | 0.015 | 0
16. | Nandur Madhmeshwar Ph-II | 121 | 115 | 0 | 115 | 0 | 0 | 0 | 0 | 115 | 95.04 | 0 | 0 | 42
17. | Sangola Branch Canal | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.00 | 8 | 0.427 | 0
18. | Tarali | 48 | 15 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 8.33 | 29 | 0 | 2
19. | Tillari | 18 | 14 | 0 | 0 | 0 | 5 | 9 | 0 | 14 | 77.78 | 18 | 0 | 5
20. | Upper Kundalika | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 7 | 0 | 0
21. | Upper Pen Ganga | 46 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 22 | 0 | 0
22. | Waghur | 78 | 68 | 0 | 0 | 6 | 15 | 47 | 0 | 68 | 87.18 | 78 | 0 | 0
 | Total | 1612 | 923 | 0 | 186 | 75 | 72 | 145 | 0 | 525 | 32.57 | 546 | 1.49 | 84
(WUA’s in Nos)
7th PIRC Meeting: Progress Review Presentations

## Slide 64
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  |  |  | 
 |  |  | Before 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (upto 07/20) | Total | % Progress
1 | Arjuna | 11.18 | 0 | 0 | 0.807 | 0 | 0 | - | 0.807 | 7.22
2. | Aruna | 9.6 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0.00
3. | Bawanthadi (IS) | 7.41 | 0 | 0 | 0.52 | 0 | 0 | - | 0.52 | 6.32
4. | Bembla | 91.42 | 0 | 0 | 5.99 | 3.51 | 0 | 2.77 | 12.27 | 19.03
5. | Dhom Balakwadi | 16.94 | 6.61 | 0 | 0 | 1.82 | 0 | 0 | 8.43 | 49.76
6. | Gadnadi | 6.1 | 0 | 0 | 0.039 | 0 | 0 | - | 0.039 | 0.64
7. | Gosikhurd (NP) | 354.09 | 0 | 0 | 0 | 9.38 | 0 | - | 9.38 | 26.49
8. | Khadakpurna | 31.46 | 0 | 0 | 2.65 | 0 | 0 | 2.39 | 5.04 | 16.10
9. | Krishna Koyana LIS | 67.38 | 0 | 0 | 3.81 | 0 | 0 | - | 3.81 | 5.65
10. | Kudali | 10.7 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0.00
11. | Lower Dudhna | 72.26 | 0 | 0 | 8.1 | 0 | 0 | - | 8.1 | 11.21
(CA in Rs. Crores)
7th PIRC Meeting: Progress Review Presentations
CA Release Progress

## Slide 65
CA Release Progress-Contd..
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  |  |  | 
 |  |  | Before 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (upto 07/20) | Total | % Progress
12. | Lower Panzara | 12.84 | 0 | 0 | 2.15 | 3.97 | 0 | 2.52 | 8.64 | 54.89
13. | Lower Pedhi | 20.50 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0.00
14. | Lower Wardha | 99.97 | 0 | 15.17 | 0 | 5.46 | 0 | 9.55 | 30.18 | 30.53
15. | Morna (Gureghar) | 8.16 | 0 | 0 | 0 | 0.28 | 0 | - | 0.28 | 3.43
16. | Nandur Madhmeshwar Ph-II | 49.26 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0.00
17. | Sangola Branch Canal | 13.83 | 0 | 0 | 0.557 | 1.37 | 0 | - | 1.927 | 13.93
18. | Tarali | 25.25 | 0 | 0 | 1.31 | 0 | 0 | 1.06 | 2.37 | 9.39
19. | Tillari | 16.10 | 0 | 0 | 1.81 | 0 | 0 | - | 1.81 | 13.77
20. | Upper Kundalika | 5.4 | 0 | 0 | 0.52 | 0 | 0 | - | 0.52 | 9.29
21. | Upper Pen Ganga | 34.83 | 0 | 0 | 3 | 0 | 0 | - | 3 | 8.61
22. | Waghur | 39.02 | 0 | 0 | 1.57 | 0 | 0 | 9.07 | 10.64 | 27.53
 | Total | 1003.70 | 6.61 | 15.17 | 32.833 | 25.79 | 0 | 27.36 | 107.76 | 10.74
(CA in Rs. Crores)
7th PIRC Meeting : Progress Review Presentations

## Slide 66
Sr. No. | Project | Targeted area under MI | CA targeted for MI (Rs. in Crore) | Micro Irrigation works Progress |  |  |  |  |  |  | 
 |  |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (upto 07/20) | Total | % Progress | Target for 2020-21
1 | Arjuna | 0.6 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4
2. | Aruna | 0.638 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.235
3. | Bawanthadi (IS) | 0.5 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
4. | Bembla | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. | Dhom Balakwadi | 1.81 | 4.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.81
6. | Gadnadi | 0.326 | 0.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.326
7. | Gosikhurd (NP) | 20.00 | 50.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.04
8. | Khadakpurna | 1.58 | 3.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.58
9. | Krishna Koyana LIS | 5.28 | 13.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.28
10. | Kudali | 2.428 | 6.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.214
11. | Lower Dudhna | 3.003 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4
(Area in Th. Ha.)
7th PIRC Meeting : Progress Review Presentations
Micro-Irrigation (MI) Progress

## Slide 67
Micro Irrigation Progress-Contd..
Sr. No. | Project | Targeted area under MI | CA targeted for MI (Rs. in Crore) | Micro Irrigation works Progress |  |  |  |  |  |  | 
 |  |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (upto 07/20) | Total | % Progress | Target for 2020-21
12. | Lower Panzara | 1.0 | 2.5 | 0 | 0 | 0 | 1.0 | 0 | 1.0 | 100 | 0
13. | Lower Pedhi | 9.77 | 24.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.66
14. | Lower Wardha | 8.4 | 14.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15. | Morna (Gureghar) | .423 | 1.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16. | Nandur Madhmeshwar Ph-II | 2.34 | 5.76 | 0 | 0 | 0.052 | 0.025 | 0 | 0.077 | 3.29 | 0
17. | Sangola Branch Canal | .690 | 1.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.345
18. | Tarali | 1.309 | 3.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19. | Tillari | .670 | 1.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20. | Upper Kundalika | 0.6 | 1.5 | 0 | 0 | 0.350 | 0.250 | 0 | 0.6 | 100 | NA
21. | Upper Pen Ganga | 1.892 | 9.46 | 0 | 0 | 0 | 0.74 | 0 | 0.74 | 39.11 | .576
22. | Waghur | 9.969 | 25.09 | 0 | 0 | 5.700 | 3.604 | 0.251 | 9.555 | 95.85 | 0.665
 | Total | 73.228 | 181.2 | 0 | 0 | 6.102 | 5.639 | 0.251 | 11.992 | 16.38 | 20.781
(Area in Th. Ha.)
7th PIRC Meeting : Progress Review Presentations

## Slide 68
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (upto 07/20) | Total | % Progress | 
1 | Arjuna | 28.94 | 0 | 0 | 0 | 2.36 | 6.63 | 8.99 | 31.06 | 4.85
2. | Aruna | 20.25 | 0 | 0 | 0.003 | 0 | 0 | 0.003 | 0.01 | 1.70
3. | Bawanthadi (IS) | 15.63 | 0.3 | 0.75 | 1.67 | 0.88 | 0.90 | 4.5 | 28.79 | 3.87
4. | Bembla | 259.85 | 0 | 9.38 | 14.87 | 16.74 | 3.28 | 44.27 | 17.04 | 15
5. | Dhom Balakwadi | 62.87 | 17.32 | 1.51 | 3.04 | 3.577 | 0.28 | 25.73 | 40.92 | 15.037
6. | Gadnadi | 19.12 | 0 | 0 | 0 | 0 | 0.0274 | 0.027 | 0.14 | 19.129
7. | Gosikhurd (NP) | 743.72 | 0 | 0 | 0 | 4.01 | 0.60 | 4.6 | 0.62 | 165.776
8. | Khadakpurna | 79.42 | 0 | 0.44 | 2.139 | 6.859 | 0.854 | 10.29 | 12.96 | 69.982
9. | Krishna Koyana LIS | 132.69 | 0 | 0 | 2.03 | 4.00 | 5.66 | 11.69 | 8.81 | 126.66
10. | Kudali | 26.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 13.71
11. | Lower Dudhna | 145.49 | 0 | 0 | 17.39 | 16.87 | 7.90 | 42.16 | 28.98 | 54.83
(TE in Rs. Crores)
7th PIRC Meeting : Progress Review Presentations
Total Expenditure Progress

## Slide 69
Total Expenditure Progress-Contd..
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (upto 07/20) | Total | % Progress | 
12. | Lower Panzara | 25.69 | 0 | 0.988 | 5.516 | 4.72 | 0.395 | 11.62 | 45.23 | 14.472
13. | Lower Pedhi | 43.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00 | 14.55
14. | Lower Wardha | 200.86 | 14.09 | 10.22 | 25.59 | 11.97 | 2.77 | 64.64 | 32.18 | 32.00
15. | Morna (Gureghar) | 16.79 | 0 | 0 | 0 | 3.35 | 0 | 3.35 | 19.95 | 1.00
16. | Nandur Madhmeshwar Ph-II | 98.5 | 0 | 1.57 | 0.09 | 2.219 | 0.216 | 4.095 | 4.16 | 11.00
17. | Sangola Branch Canal, | 32.44 | 0 | 0.58 | 0.56 | 0 | 0 | 1.14 | 3.51 | 15.65
18. | Tarali | 53.63 | 0 | 0 | 0.17 | 12.02 | 0 | 12.19 | 22.73 | 41.45
19. | Tillari | 32.45 | 0 | 0.8 | 0.95 | 0.18 | 2.34 | 4.27 | 13.16 | 9.00
20. | Upper Kundalika | 14.25 | 0 | 0 | 6.76 | 2.31 | 0.065 | 9.135 | 64.11 | 5.56
21. | Upper Pen Ganga | 69.62 | 0 | 3.817 | 4.458 | 2.310 | 4.99 | 15.578 | 22.37 | 20
22. | Waghur | 78.04 | 0.09 | 1.09 | 29.50 | 19.39 | 3.399 | 53.47 | 68.51 | 27.97
 | Total | 2200.89 | 31.80 | 31.145 | 114.736 | 113.765 | 40.306 | 331.752 | 15.07 | 683.2
(TE in Rs. Crores)
7th PIRC Meeting: Progress Review Presentations

## Slide 70
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016* (A) | Progress in CCA for 99 Priority Projects (upto 07/20) (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created (upto 07/20) | % IPC
1 | Arjuna | 5.704 | 0 | 0 | 0.00 | 0 | 5.7 | 2.07 | 36.32
2. | Aruna | 5.31 | 0 | 0 | 0.00 | 0 | 11.71 | 0 | 0.00
3. | Bawanthadi (IS) | 25.66 | 23.16 | 1.63 | 24.79 | 96.61 | 27.71 | 27.71 | 100.00
4. | Bembla | 40.17 | 10.39 | 11.142 | 21.53 | 53.6 | 52.54 | 43.354 | 82.52
5. | Dhom Balaakwadi | 18.1 | 10.07 | 15.616 | 25.69 | 141.9 | 18.1 | 16.203 | 89.52
6. | Gadnadi | 3.111 | 0 | 0.025 | 0.03 | 0.804 | 3.47 | 0.43 | 12.39
7. | Gosikhurd (NP) | 190 | 13.89 | 0 | 13.89 | 7.311 | 250.8 | 115.587 | 46.09
8. | Khadakpurna | 23.9 | 8.18 | 6.691 | 14.87 | 62.22 | 24.86 | 22.85 | 91.91
9. | Krishna Koyana LIS | 52.82 | 0 | 5.794 | 5.79 | 10.97 | 104.17 | 82.24 | 78.95
10. | Kudali | 5.327 | 0 | 0 | 0.00 | 0 | 5.33 | 0.37 | 6.94
11. | Lower Dudhna | 44.48 | 14.44 | 14.271 | 28.71 | 64.55 | 44.48 | 43.889 | 98.67
(CCA in Th. ha.)
7th PIRC Meeting : Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.
Broad Review

## Slide 71
Broad Review-Contd..
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (upto 07/20) (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created (upto 07/20) | % IPC
12. | Lower Panzara | 6.785 | 0 | 6.26 | 6.26 | 92.26 | 6.79 | 6.79 | 100.00
13. | Lower Pedhi | 10.19 | 0 | 0 | 0.00 | 0 | 19.3 | 0 | 0.00
14. | Lower Wardha | 63.33 | 2.13 | 28.994 | 31.12 | 49.15 | 63.33 | 44.15 | 69.71
15. | Morna (Gureghar) | 4.229 | 0 | 0 | 0.00 | 0 | 3.08 | 1.51 | 49.03
16. | Nandur Madhmeshwar Ph-II | 52.86 | 29.75 | 1.957 | 31.71 | 60.09 | 20.5 | 20.5 | 100.00
17. | Sangola Branch Canal | 6.883 | 0 | 0.149 | 0.15 | 2.165 | 11.29 | 9.01 | 79.81
18. | Tarali | 15.83 | 2.744 | 5.579 | 8.32 | 52.58 | 14.28 | 8.782 | 61.50
19. | Tillari | 6.676 | 0 | 0.617 | 0.62 | 9.391 | 6.676 | 6.131 | 91.84
20. | Upper Kundalika | 2.8 | 0 | 2.55 | 2.55 | 91.07 | 2.8 | 2.8 | 100.00
21. | Upper Pen Ganga | 104 | 86.71 | 5.445 | 92.16 | 88.61 | 44.47 | 32.08 | 72.14
22. | Waghur | 17.97 | 0 | 10.974 | 10.97 | 61.07 | 38.57 | 31.416 | 81.45
 | Total | 706.14 | 201.464 | 117.694 | 319.16 | 45.20 | 779.96 | 517.87 | 66.40
(CCA in Th. ha.)
7th PIRC Meeting : Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 72
Glimpses of CAD Works Progress
7th PIRC Meeting : Progress Review Presentations
Upper Penganga Project

## Slide 73
Glimpses of CAD Works Progress
7th PIRC Meeting : Progress Review Presentations
Tillari Project
Arjuna Project

## Slide 74
Glimpses of CAD Works Progress
7th PIRC Meeting : Progress Review Presentations
Lower Panzara Project

## Slide 75
Glimpses of CAD Works Progress
7th PIRC Meeting : Progress Review Presentations
KKLIS Project
Bawanthandi Project

## Slide 76
Key Bottlenecks in Progress
Status | Key Bottlenecks
1 | Opposition of marginal farmers for land acquisition.
2 | Shorter available working period due to standing two seasonal crops
3 | Absence of hydraulic-continuity in distribution network creation
4 | Non-availability of natural sand
5 | Shortage of manpower at working level related issues of State Implementing Agencies.
6 | Delay in Planning, Approval and Tendering of works.
7 | Capacity related issues of Contractors/Suppliers.
8 | State Budget/Funds constraints.
7th PIRC Meeting : Progress Review Presentations

## Slide 77
7th PIRC Meeting: Progress Review Presentations
Physical & Financial Progress achieved in the projects between 6th & 7th PIRC meeting
Component-wise physical progress in CAD work
Extra Slides

## Slide 78
Sr. No. | Project | CCA (In Th. ha) |  |  |  | Expenditure (In Cr.) |  |  | 
 |  | 6th PIRC Meeting (Upto 02/20) | 7th PIRC Meeting (Upto 07/20) | Progress | % Progress | 6th PIRC Meeting (Upto 02/20) | 7th PIRC Meeting (Upto 07/20) | Progress | % Progress
1 | Arjuna | 0.00 | 0 | 0 | 0 | 0.00 | 8.99 | 8.99 | 899
2. | Aruna | 0.00 | 0 | 0 | 0 | 0.00 | 0.003 | 0.003 | 0.30
3. | Bawanthadi (IS) | 1.29 | 1.63 | 0.34 | 26.36 | 3.31 | 4.5 | 1.19 | 35.952
4. | Bembla | 7.515 | 11.142 | 3.627 | 48.26 | 34.76 | 44.27 | 9.51 | 27.359
5. | Dhom Balaakwadi | 15.184 | 15.616 | 0.432 | 2.84 | 24.98 | 25.73 | 0.75 | 3.0024
6. | Gadnadi | 0.00 | 0.025 | 0.025 | 2.5 | 0.00 | 0.027 | 0.027 | 2.70
7. | Gosikhurd (NP) | 0.00 | 0 | 0 | 0 | 2.944 | 4.6 | 1.656 | 56.25
8. | Khadakpurna | 5.843 | 6.691 | 0.848 | 14.51 | 9.091 | 10.29 | 1.199 | 13.189
9. | Krishna Koyana LIS | 3.402 | 5.794 | 2.392 | 70.31 | 2.55 | 11.69 | 9.14 | 358.43
10. | Kudali | 0.00 | 0 | 0 | 0 | 0.00 | 0 | 0 | 0
11. | Lower Dudhna | 9.813 | 14.271 | 4.458 | 45.43 | 31.02 | 42.16 | 11.14 | 35.912
7th PIRC Meeting: Progress Review Presentations
Status of Physical & Financial Progress in between 6th & 7th PIRC

## Slide 79
Sr. No. | Project | CCA (In ha) |  |  |  | Expenditure (In Cr.) |  |  | 
 |  | 6th PIRC Meeting (Upto 02/20) | 7th PIRC Meeting (Upto 07/20) | Progress | % Progress | 6th PIRC Meeting (Upto 02/20) | 7th PIRC Meeting (Upto 07/20) | Progress | % Progress
12. | Lower Panzara | 5.210 | 6.26 | 1.05 | 20.15 | 10.961 | 11.62 | 0.659 | 6.01
13. | Lower Pedhi | 0.00 | 0 | 0 | 0 | 0.00 | 0 | 0 | 0
14. | Lower Wardha | 25.180 | 28.994 | 3.81 | 15.15 | 58.07 | 64.64 | 6.57 | 11.31
15. | Morna (Gureghar) | 0.00 | 0 | 0 | 0 | 0.133 | 3.35 | 3.217 | 2418.8
16. | Nandur Madhmeshwar Ph-II | 1.487 | 2.012 | 0.52 | 35.31 | 3.8554 | 4.095 | 0.2396 | 6.21
17. | Sangola Branch Canal | 0.149 | 0.149 | 0 | 0 | 1.14 | 1.14 | 0 | 0
18. | Tarali | 2.55 | 5.579 | 3.03 | 118.78 | 8.21 | 12.19 | 3.98 | 48.48
19. | Tillari | 0.424 | 0.617 | 0.19 | 45.52 | 2.915 | 5.25 | 2.335 | 80.10
20. | Upper Kundalika | 2.55 | 2.55 | 0 | 0 | 8.68 | 9.135 | 0.455 | 5.24
21. | Upper Pen Ganga | 3.298 | 5.445 | 2.15 | 65.1 | 20.21 | 25.12 | 4.91 | 24.29
22. | Waghur | 10.420 | 10.974 | 0.55 | 5.32 | 50.056 | 53.47 | 3.414 | 6.82
 | Total | 94.31 | 117.749 | 23.434 | 24.87 | 272.88 | 342.27 | 69.38 | 25.43
7th PIRC Meeting: Progress Review Presentations
Status of Physical & Financial Progress in between 6th & 7th PIRC

## Slide 80
Sr. No | Project | Total Quantity | Area created (upto 07/2020) | Component wise progress upto 07/2020 |  |  |  |  |  |  | 
 |  |  |  | Field Channel/ PDN | Created | Micro Irrigation | Created | Correction in System Deficiency | Created | Reclamation of Water logged areas | Created
1 | Arjuna | 5.704 | 0 | 5.107 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0
2. | Aruna | 5.31 | 0 | 4.672 | 0 | 0.638 | 0 | 0 | 0 | 0 | 0
3. | Bawanthadi (IS) | 2.5 | 1.63 | 2.0 | 1.63 (81.5%) | 0.5 | 0 | 1.0 | 0 | 0 | 0
4. | Bembla | 29.78 | 11.14 | 29.78 | 11.14 (37.41%) | 0 | 0 | 4.02 | 0 | 4.02 | 0
5. | Dhom Balakwadi | 18.10 | 15.62 | 18.10 | 15.62 (86.30%) | 0 | 0 | 0 | 0 | 0 | 0
6. | Gadnadi | 3.111 | 0.025 | 2.785 | 0.025 (0.9%) | 0.326 | 0 | 0 | 0 | 0 | 0
7. | Gosikhurd (NP) | 176.1 | 0 | 15.6107 | 0 | 20.0 | 0 | 10.0 | 0 | 2.0 | 0
8. | Khadakpurna | 15.72 | 6.691 | 14.14 | 6.691 (47.32%) | 1.58 | 0 | 3.5 | 0 | 1.2 | 0
(Area in Th. Ha.)
7th PIRC Meeting: Progress Review Presentations
Component wise progress

## Slide 81
Sr. No | Project | Total Quantity | Area created (upto 07/2020) | Component wise work Progress upto 07/2020 |  |  |  |  |  |  | 
 |  |  |  | Field Channel/ PDN | Created | Micro Irrigation | Created | Correction in System Deficiency | Created | Reclamation of Water logged areas | Created
9. | Krishna Koyana LIS | 52.82 | 5.794 | 47.544 | 5.794 (12.19%) | 5.28 | 0 | 0 | 0 | 0 | 0
10. | Kudali | 5.327 | 0 | 36.4 | 0 | 2.428 | 0 | 0 | 0 | 0 | 0
11. | Lower Dudhna | 30.04 | 14.271 | 27.032 | 14.271 (52.79%) | 3.003 | 0 | 17.21 | 0 | 0.86 | 0
12. | Lower Panzara | 6.785 | 6.26 | 5.785 | 5.26 (90.92%) | 1.0 | 1.0 (100.0%) | 0 | 0 | 0.1 | 0
13. | Lower Pedhi | 10.19 | 0 | 0 | 0 | 9.77 | 0 | 0 | 0 | 0 | 0
14. | Lower Wardha | 62.45 | 28.994 | 54.053 | 28.994 (53.64%) | 8.4 | 0 | 3.75 | 0 | 3.0 | 0
15. | Morna (Gureghar) | 4.229 | 0 | 3.806 | 0 | 2.34 | 0 | 0 | 0 | 0 | 0
16. | Nandur Madhmeshwar Ph-II | 23.12 | 1.957 | 20.812 | 1.88 (9.03%) | 0.423 | 0.077 (18.20%) | 18.0 | 0 | 0.5 | 0
(Area in Th. Ha.)
7th PIRC Meeting: Progress Review Presentations
Component wise progress -Contd..

## Slide 82
Component wise progress -Contd..
Sr. No. | Project | Total Quantity | Area created (upto 07/2020) | Component wise works Progress upto 07/2020 |  |  |  |  |  |  | 
 |  |  |  | Field Channel/ PDN | Created | Micro Irrigation | Created | Correction in System Deficiency | Created | Reclamation of Water logged areas | Created
17. | Sangola Branch Canal | 6.883 | 0.149 | 6.193 | 0.149 (2.41%) | 0.690 | 0 | 0 | 0 | 0.05 | 0
18. | Tarali | 13.09 | 5.579 | 11.777 | 5.579 (47.31%) | 1.309 | 0 | 0 | 0 | 0 | 0
19. | Tillari | 6.68 | 0.617 | 6.01 | 0.617 (10.26%) | 0.670 | 0 | 4.01 | 1.16 (28.93%) | 0.2 | 0
20. | Upper Kundalika | 2.8 | 2.55 | 2.20 | 1.95 (8.86%) | 0.6 | 0.6 (100.0%) | 0 | 0 | 0 | 0
21. | Upper Pen Ganga | 17.29 | 5.445 | 15.397 | 4.715 (30.62%) | 1.892 | 0.740 (39.11%) | 0 | 0 | 0 | 0
22. | Waghur | 17.97 | 10.974 | 8.003 | 1.419 (17.73%) | 9.969 | 9.555 (98.54%) | 0 | 0 | 0 | 0
 | Total | 515.99 | 117.749 | 337.21 | 105.73 (31.35%) | 71.418 | 11.97 (16.76%) | 61.49 | 1.16 (1.89%) | 11.93 | 0 (0%)
(Area in Th. Ha.)
7th PIRC Meeting: Progress Review Presentations

## Slide 83
Thank you

## Slide 84
Mahi & Tapi Basin Organisation
GANDHINAGAR
Aug 11, 2020
Status of
PMKSY- CAD&WM WORKS
For
Sardar Sarovar (Narmada) Project, Gujarat
7th PIRC Meeting

## Slide 85: Minor and chak layout

## Slide 86
Gujarat
Number of Projects : 1 Projects Included: 1 Projects Availing CA: 1 Projects Reporting Progress:1
Physical Progress
7th PIRC Meeting : Progress Review Presentations
CA
(Rs. Crore)
WUA
(Nos.)
CCA
(Th. Ha)

## Slide 87
State and Year wise CCA Progress
Sr. No. | Project Total CCA | Balance outstanding CCA as on 1-April-2016 | CCA Progress |  |  |  |  |  | 
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (upto July-20) | Total | % of CCA Progress
1 | 1792.00 | 1363.859 | 385.330 | 290.061 | 260.165 | 1.593 | 1.463 | 938.612 | 68.82
 | TOTAL | 1363.859 | 385.330 | 290.061 | 260.165 | 1.593 | 1.463 | 938.612 | 68.82
( Area in Th. Ha.)
7th PIRC Meeting: Progress Review Presentations

## Slide 88
In Gujarat, the Micro Irrigation System (MIS) is carried out by Gujarat Green Revolution Company Ltd. (Under taking of Government of Gujarat) for individual farmer as per government subsidy base. So, there is no role of SSNNL for MIS in Gujarat.
Micro Irrigation Target and Progress
7th PIRC Meeting : Progress Review Presentations

## Slide 89
No. of WUA Registered, handed over & functional grant given
Sr. No. | WUA Target | No. of WUA Registered |  |  |  |  |  |  |  | Target for 2020-21
 |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (upto July-20) | Total | % Progress | 
1 | 4466 | 1894 | 428 | 46 | 528 | 414 | 24 | 3334 | 74.65 | 700
7th PIRC Meeting : Progress Review Presentations
Sr. No. | WUA Target | No. of WUA Handed over |  |  |  |  |  |  |  | Target for 2020-21
 |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (upto July-20) | Total | % Progress | 
1 | 4466 | 365 | 220 | 426 | 204 | 219 | 6 | 1440 | 32.24 | 600
Sr. No. | WUA Target | Functional grant given to WUA (Rs. in Lakhs) |  |  |  |  |  | 
 |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total
1 | 4466 | Rs. 273.30 lakhs to 110 WUAs. |  |  |  |  |  | 273.30

## Slide 90
Year-wise CA Release Progress
Sr. No. | Overall CA Target | CA Release Progress |  |  |  |  |  |  |  | Target for 2020-21
 |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
1 | 251088.30 | 0 | 68163.87 | 69047.60 | 34704.00 | 0 | 0 | 171915.47 | 68.47 | 34000.00
 | 251088.30 | 0 | 68163.87 | 69047.60 | 34704.00 | 0 | 0 | 171915.47 | 68.47 | 34000.00
(CA in Rs. Lakhs)
7th PIRC Meeting: Progress Review Presentations

## Slide 91
Total Financial Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (upto June-20) | Total | % Progress | 
1 | Sardar Sarovar Project | 502176.50 | 143590.60 | 122472.90 | 86168.00 | 7695.86 | 901.207 | 360828.567 | 71.85 | 74091.00
 | TOTAL | 502176.50 | 143590.60 | 122472.90 | 86168.00 | 7695.86 | 901.207 | 360828.567 | 71.85 | 74091.00
(Rs. Lakhs)
7th PIRC Meeting: Progress Review Presentations

## Slide 92
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed as on 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created upto June-20 | % IPC
1 | Sardar Sarovar Project | 1792.000 | 551.802 | 938.612 | 1490.414 | 83.17 | 1792 | 1671.607 | 93.28
 | TOTAL | 1792.000 | 551.802 | 938.612 | 1490.414 | 83.17 | 1792 | 1671.607 | 93.28
(CCA in Th. ha.)
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.
7th PIRC Meeting : Progress Review Presentations

## Slide 93
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
X | Delay in Govt/Administrative clearances.
X | State budget constraints.
√ | Unwillingness of farmers.
√ | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
√ | Other Issue (to be specified) – Covid-19
7th PIRC Meeting : Progress Review Presentations

## Slide 94
LAYOUT SHOWING SARDAR SAROVAR CANAL NETWORK AND BOTTLENECK AREAS

## Slide 95
LAYOUT SHOWING KACHCHH BRANCH CANAL NETWORK AND BOTTLENECK AREAS

## Slide 96
THANK YOU

## Slide 97
STATE :ODISHA
Status of
PMKSY- CAD&WM Works
For
7th PIRC meeting
through virtual Platform
on 11.09.2020
Government of Odisha
Department of Water Resources

## Slide 98
Total Projects : 8 Nos
Completed : 03 nos

## Slide 99
CCA Progress
Project Name | Balance CCA Target | CCA Progress |  |  |  | Total Achvt. | % of Progress | 2020-21 | 
 |  |  |  |  |  |  |  | Target | Achvt. Aug,20
 |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 |  |  |  | 
Upper Indravati Extn. | 23.83 | 5.35 | 18.48 | 0.00 | - | 23.83 | 100% | - | -
Ret | 8.50 | 0.00 | 2.42 | 6.08 | - | 8.50 | 100% | - | -
Rukura | 5.75 | 1.38 | 2.88 | 1.18 | 0.21 | 5.65 | 98% | - | -
Lower Indra | 29.90 | 0.00 | 0.00 | 10.02 | 7.38 | 17.40 | 58% | 9.51 | 1.15
Telengiri | 9.95 | 0.00 | 0.00 | 0.86 | 7.03 | 7.89 | 79% | 2.06 | 1.33
Subarnarekha | 68.83 | 2.76 | 1.70 | 0.09 | 0.08 | 4.63 | 7% | 1.76 | 0
Anandapur | 60.00 | 0.00 | 1.51 | 0.30 | 0.28 | 2.08 | 4% | 0.92 | 0.14
Kanupur | 29.58 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0% | 0.00 | 0.00
Total | 236.34 | 9.49 | 26.99 | 18.67 | 14.98 | 69.98 | 30% | 14.25 | 2.62
Area in Th.ha
Odisha

## Slide 100
WUA Progress (Formed)
Project Name | WUA Target | WUA Progress |  |  |  | Total Achvt*. | % of Progress | 2020-21 | 
 |  |  |  |  |  |  |  | Target | Achivt. Upto Aug,20
 |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 |  |  |  | 
Upper Indravati Extn. | 59 | 0 | 59 | 0 | 0 | 59 | 100% | - | -
Ret | 19 | 0 | 0 | 19 | 0 | 19 | 100% | - | -
Rukura | 15 | 3 | 10 | 2 | 0 | 15 | 100% | - | -
Lower Indra | 75 | 0 | 0 | 0 | 0 | 0 | 0% | 75 | 0
Telengiri | 22 | 0 | 0 | 0 | 0 | 0 | 0% | 22 | 0
Subarnarekha | 156 | 13 | 0 | 6 | 4 | 23 | 15% | 0 | 0
Anandapur | 133 | 0 | 0 | 0 | 0 | 0 | 0% | 8 | 0
Kanupur | 66 | - | - | - | 0 | 0 | 0% | 0 | 0
Total | 545 | 16 | 69 | 27 | 4 | 116 | 21% | 105 | 0
WUA’s in Nos.
Odisha
NB: * Formation of WUA has been formed as per Pani Panchayat Act of Government of Odisha.

## Slide 101
WUA Progress
Project Name | WUA Target | Total *(Formed) | Total (Handed over) | Functional Grant released (in Cr.)
Upper Indravati Extn. | 59 | 59 | 59 | 2.46
Ret | 19 | 19 | 19 | 0.00**
Rukura | 15 | 15 | 15 | 0.055
Lower Indra | 75 | 0 | 0 | 0.00
Telengiri | 22 | 0 | 0 | 0.00
Subarnarekha | 156 | 23 | 0 | 0.00
Anandapur | 133 | 0 | 0 | 0.00
Kanupur | 66 | 0 | 0 | 0.00
Total | 545 | 116 | 93 | 2.515
WUA’s in Nos.
Odisha
NB: * WUA has been formed as per Pani Panchayat Act of Government of Odisha.
** Functional Grant will be released after receiving farmers share, which is under process.

## Slide 102
CA Release Progress
Project Name | Overall CA Target | CA Release Progress |  |  |  |  | % of Progress | Balance CA
 |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | Total |  | 
Upper Indravati Extn. | 44.03 | 8.50 | 30.83 | 0.00 | 0.00 | 39.33 | 89.33% | 4.71
Ret | 16.55 | 0.00 | 4.11 | 0.00 | 9.11 | 13.21 | 79.88% | 3.34
Rukura | 10.21 | 2.41 | 0.80 | 0.00 | 0.58 | 3.79 | 37.12% | 6.42
Lower Indra | 51.67 | 24.37 | 0.00 | 0.00 | 7.58 | 31.95 | 61.83% | 18.82
Telengiri | 16.72 | 0.00 | 2.84 | 0.00 | 4.75 | 7.59 | 45.39% | 9.13
Subarnarekha | 126.03 | 0.00 | 16.28 | 0.00 | 0.00 | 16.29 | 12.92% | 109.74
Anandapur | 101.57 | 0.00 | 1.82 | 0.00 | 0.00 | 1.82 | 1.79% | 99.75
Kanupur | 53.44 | 0.00 | 1.89 | 3.65 | 0.00 | 5.54 | 10.37% | 47.90
Total | 420.22 | 35.28 | 58.57 | 3.65 | 22.02 | 119.52 | 28.44% | 299.81
CA in Rs. Cr.
Odisha
During 2020-21, CA proposal of 05 projects namely Anandapur, Lower Indra, Ret, Subarnarekha & Telengiri submitted. But, Central Assistance has not yet been released.

## Slide 103
Total Expenditure Progress
Project Name | Total Estimate | Total Expenditure Incurred |  |  |  | Total Achvt. | % of Progress | 2020-21 | 
 |  |  |  |  |  |  |  | BE | Achivt. Upto Aug,20
 |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 |  |  |  | 
Upper Indravati Extn. | 140.27 | 43.43 | 65.85 | 13.14 | 2.89 | 125.31 | 89% | - | -
Ret | 46.87 | 0.66 | 8.13 | 28.64 | 2.72 | 40.15 | 86% | 3.80 | 0.52
Rukura | 31.71 | 4.82 | 11.06 | 5.12 | 1.66 | 22.66 | 71% | 0.05 | 0.01
Lower Indra | 103.08 | 2.00 | 0.00 | 39.18 | 31.14 | 72.32 | 70% | 19.29 | 1.38
Telengiri | 54.51 | 0 | 0.25 | 6.94 | 36.31 | 43.50 | 80% | 11.50 | 7.16
Subarnarekha | 389.58 | 7.85 | 11.95 | 12.98 | 4.53 | 37.31 | 10% | 12.07 | 0.48
Anandapur | 334.37 | 0.00 | 2.08 | 2.09 | 3.30 | 7.47 | 2% | 9.00 | 0.96
Kanupur | 164.85 | 0.00 | 1.45 | 1.28 | 0.00 | 2.73 | 2% | 0.29 | 0.00
Total | 1265.24 | 58.76 | 100.77 | 109.37 | 82.55 | 351.45 | 27% | 56.00 | 10.51
TE in Rs. Cr.
Odisha

## Slide 104
STATUS OF LTIF RELEASED BY NABARD AS STATE SHARE
Project Name | Eligible State under LTIF | Amount Released so far | % of released
Upper Indravati Extn. | 96.24 | 88.31 | 92%
Ret | 30.32 | 25.94 | 86%
Rukura | 21.50 | 13.93 | 42%
Lower Indra | 51.41 | 30.96 | 60%
Telengiri | 37.79 | 19.73 | 52%
Subarnarekha | 263.55 | 19.52 | 7.4%
Anandapur | 232.79 | 3.49 | 1.5%
Kanupur | 111.41 | 0.00 | 0%
Total | 845.01 | 201.88 | 24%
Amount in Cr.
Odisha

## Slide 105
Micro Irrigation Progress
Project Name | Target | Achievement upto August, 2020 | Remarks
Upper Indravati Extn. | 2.548 | 0.000 | Not done. The area was covered under field channel.
Ret | 0.850 | 0.000 | Not done. The area was covered under field channel
Rukura | 0.575 | 0.252 | 370 ha of area identified.
Lower Indra | 2.990 | 0.000 | Under execution.
Telengiri | 0.995 | 0.000 | Not done. The area was covered under field channel
Subarnarekha | 6.993 | 0.000 | Not finalized
Anandapur | 6.000 | 0.000 | Not finalized
Kanupur | 3.078 | 0.000 | Not finalized.
Total | 24.029 | 0.252 | 
Area in Th. Ha
Odisha
NB: The concept of Micro Irrigation has been adopted in Mega lift Projects

## Slide 106
Broad Review
CCA in Th.ha
Project Name | CAD&WM |  |  |  |  | AIBP |  | 
 | Total CCA of the Project | CCA developed before 31.03.2016(A*) | Progress in CCA for 99 priority Projects (B), Aug, 20 | Cumulative CCA developed (A+B) | % CCA progress | Ultimate Irrigation Potential | Potential Created upto Aug, 20 | % of IPC
Upper Indravati Extn. | 25.48 | 1.65 | 23.83 | 25.48 | 100% | 41.794 | 41.79 | 100%
Ret | 8.50 | 0 | 8.50 | 8.50 | 100% | 9.78 | 9.78 | 100%
Rukura | 5.75 | 0 | 5.65 | 5.65 | 98% | 7.65 | 7.08 | 89%
Lower Indra | 29.90 | 0 | 18.55 | 18.55 | 62% | 38.87 | 36.40 | 94%
Telengiri | 9.95 | 0 | 8.36 | 8.36 | 84% | 13.79 | 12.30 | 89%
Subarnarekha | 69.80 | 1.10 | 4.63 | 5.73 | 8% | 115.26 | 77.97 | 68%
Anandapur | 60.00 | 0 | 2.22 | 2.22 | 3.7% | 56.72 | 3.00 | 5%
Kanupur | 29.58 | 0 | 0.00 | 0.00 | 0% | 47.71 | 0.00 | 0%
Total | 238.96 | 2.75 | 64.76 | 67.51 | 28% | 331.57 | 188.32 | 56%
Odisha

## Slide 107
Field Channel under construction
Rukura Irrigation Project
Upper Indravati Extension
Field Channel under construction

## Slide 108
Lower Indra Irr.Project (OFD works)
UGPL Single Outlet
Pipe laying at Distributaries
Testing of Khariff water supply in UGPL system
UGPL Double Outlet

## Slide 109
Rukura Irrigation Project
Aerial View of CAD&WM works

## Slide 110
Subarnarekha Irr. Project
Ret Irrigation Project

## Slide 111
Anandapur Barrage Project
Barrage Impounding

## Slide 112
Key Reasons for Progress delay
Covid-19 Pandemic delayed the progress of CAD&WM of all Projects.
Odisha

## Slide 114
MONITORING SOUTH ORGANISATION
CENTRAL WATER COMMISSION, BENGALURU
7th Project Implementation Review Committee (PIRC) for CADWM Implementation under 99 PRIORITIZED PROJECTS- Karnataka State
Date -11th September,2020

## Slide 115
Karnataka
Number of Projects included: 5 Projects Availing CA: 4
7th PIRC Meeting Progress Review Presentations
Sri Rameshwara LIS (Belagavi)
Upper Tunga Project (Shivomoga)
Bhima LIS (Kalburgi)
4. Karanja Project (Kalburgi)
5. NLBC – State Govt. proposed to drop this project during 6th PIRC
Notes: CADWM works of NLBC did not pick up hence dropped. Proposed CCA- 28.67 Th Hect.; Cost 750 Cr--- State share 687.83 Cr + central share 62.17 cr.

## Slide 116
Source: Gataprabha River
Utilisation: 62.3MCM (2.2TMC)
CCA:13,800Ha
Source: Tunga River
Utilisation:346.51MCM (12.24TMC)
CCA: 80,494 Ha
Source: Bhima River
Utilisation:169.90MCM (6.00TMC)
CCA: 24,292Ha
Source: Karanja River
Utilisation:285.71MCM
(10.09TMC)
CCA: 29,277 Ha
SHRI RAMESHWARA LIS
UPPER TUNGA PROJECT
BHIMA LIS
KARANJA PROJECT
INDEX MAP SHOWING THE CCA OF PROJECTS UNDER PMKSY- CADWM

## Slide 117
Karnataka
7th PIRC Meeting Progress Review Presentations
Chart: 
| Financial Target ( In Crores) | Total Financial Progress ( In Crores) | Over All CA Target ( In Crores) | Total CA Release ( In Crores)
Financial Progress | 0 | 0 | 0 | 0
Financial Target ( In Crores) Total Financial Progress ( In Crores) Over All CA Target ( In Crores) Total CA Release ( In Crores) | 253.51 | 158.166 | 113.71 | 72.63
Chart: 
| Balance outstanding CCA (Th.Ha) | Total CCA Porgress (Th.Ha) | No. of Targeted WUA | Total WUA Progress
Physical Progress | 0 | 0 | 0 | 0
Balance outstanding CCA (Th.Ha) Total CCA Porgress (Th.Ha) No. of Targeted WUA Total WUA Progress | 55.35 | 36.7475 | 264 | 179

## Slide 118
CCA Progress
7th PIRC Meeting Progress Review Presentations
Area in Th.Ha
Sl. No. |  | Project Name | Project Total CCA (Th.Ha) | Balance Outstanding CCA as on 01 April 2016 (Th.Ha) | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | Programme for 2020-21 | Progress during 2020-21 | Total CCA Porgress | % of CCA Progress
 |  |  |  |  | (Th.Ha) | (Th.Ha) | (Th.Ha) | (Th.Ha) | (Th.Ha) | (Th.Ha) | (Th.Ha) |  | 
1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 |  | Sri Rameshwara LIS / Belagavi | 13.8 | 11.418* | 2.037 | 4.857 | 1.294 | 2.715 | 0 | 0 | 0 | 10.903 | 95.49%
2 |  | Upper Tunga/ Shivamogga | 80.494 | 25.449 | 0 | 2.828 | 4.287 | 2.119 | 1.681 | 14.44 | 0.09 | 11.005 | 43.24%
3 |  | Bhima LIS / Kalaburgi | 24.292 | 12.898** | 0 | 3.396 | 5.372 | 2.754 | 0.051 | 0.05 | 0.05 | 11.623 | 90.11%
4 |  | Karanja/ Kalaburagi | 29.227 | 5.588 | 0 | 0 | 0 | 1.304 | 2.053 | 2.23 | 0 | 3.357 | 60.08%
Total |  |  | 147.81 | 55.353 | 2.037 | 11.081 | 10.953 | 8.892 | 3.785 | 16.72 | 0.09 | 36.838 | 66.55%
* | Since farmers have created their own irrigation during implementation of the project, FIC cannot be created for an balance area of 514 Ha, | FIC cannot be created for an balance area of 514 Ha, because farmers have created their own source of irrigation during implementation of the project of which they are not ready to accept FIC in their land. |  |  |  |  |  |  |  |  |  |  | 
** | An area of 1284.00 Ha is going to under micro irrigation as informed by project authorities . Farmers/ location have been identified. Waiting for administrative approval from WRD. | Pertaining to Bhima LIS - An area of 1284.00 Ha is going to take up under micro irrigation as informed by project authorities . Farmers and location have been identified and waiting for administrative approval from WRD. |  |  |  |  |  |  |  |  |  |  | 
Notes: Slow progress of UTP CADWM is due to slow progress of AIBP WORKS.
AIBP works of UTP are delaying due to delay in compensastion for land acquisition, approval of revised estimate. Earlier railway crossing at 232 km, highway crossing at 231.942 km and halt of works due heavy rains last year delayed it.
Karanja was included in 2018. They have shown good progress during last year, and hence will complete works this year.

## Slide 119
Project and Year-wise MI Progress
7th PIRC Meeting Progress Review Presentations
Area in Th.Ha
Project Name | Targeted MI CCA (Th. Ha) | CA Targeted For MI (Rs.) | MI works under Taken (as per CA Proposal) |  |  | Progress CCA | % of MI Progress
 |  |  | 2016-17 (Th.Ha) | 2017-18 (Th.Ha) | 2018-19 (Th.Ha) |  | 
Sri Rameshwara LIS | MI is dropped as per revised MoU |  |  |  |  |  | 
Upper Tunga |  |  |  |  |  |  | 
Bhima LIS |  |  |  |  |  |  | 
Karanja | MI was not proposed in this project |  |  |  |  |  | 

## Slide 120
WUA Progress
(WUA’s in No’s)
7th PIRC Meeting Progress Review Presentations
Sl. No. | Project | No. of Targeted WUA | No. of WUA Created before April 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | Total | % Progress | Programme for 2020-21
1 | Sri Rameshwara LIS / Belagavi | 22 | 0 | 1 | 9 | 6 | 4 | 20 | 90.91% | 2
2 | Upper Tunga/ Shivamogga | 186 | 0 | 0 | 48 | 66 | 0 | 114 | 61.29% | 72
3 | Bhima LIS / Kalaburgi | 47 | 0 | 0 | 38 | 2 | 3 | 43 | 91.49% | 4
4 | Karanja/ Kalaburagi | 60 | 48 | 0 | 0 | 3 | 3 | 54 | 90.00% | 6
Total |  | 315 | 48 | 1 | 95 | 77 | 10 | 231 | 83.42% | 84

## Slide 121
WUCS – Registered, Handed over, OTFG and Infrastructure Grant details
7th PIRC Meeting Progress Review Presentations
SL. No. | Activity | Unit | Sri Rameshwara LIS |  | Upper Tunga/ |  | Bhima LIS / |  | Karanja/ |  | Total | 
 |  |  | CADA Belagavi |  | CADA Shivamogga |  | CADA Kalaburgi |  | CADA Kalaburagi |  |  | 
 |  |  | Total | Progress | Total | Progress | Total | Progress | Total | Progress | Total Target | Progress
 |  |  | Target |  | Target |  | Target |  | Target |  |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Formation of WUCS (registration) | No's | 22 | 20 | 186 | 114 | 47 | 43 | 60 | 6 | 315 | 231
2 | Handed over (MoU) | No's | 22 | 18 | 186 | 15 | 47 | 24 | 9 | 0 | 264 | 57
3 | One time Fuctinoal Grant (OTFG) to WUCS | Ha | 13800 | 9276 | 25449 | 1665 | 24292 | 8790 | 5588 | 0 | 69129 | 19731
 |  | Fin (lakhs) | 165.6 | 93.78 | 305.39 | 17.97 | 291.5 | 43.44 | 67.06 | 0 | 829.6 | 155.2
4 | Infrastructure grant to WUCs | No's | 22 | 0 | 186 | 0 | 47 | 5 | 9 | 0 | 264 | 5
 |  | Fin (lakhs) | 66 | 10.20 | 558 | 7.43 | 141 | 15 | 27 | 0 | 792 | 32.63

## Slide 122
CA Release Progress
(CA in Rs. Crores)
7th PIRC Meeting Progress Review Presentations
Sl. No. | Project Name | Over All CA Target | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | Total CA Release | % of CA Release Progress | Target for 2020-21
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | Sri Rameshwara LIS / Belagavi | 22.99 | 1.41 | 10.38 | 2.50 | 3.87 | 0.00 | 18.16 | 79% | 4.83
2 | Upper Tunga/ Shivamogga | 55.86 | 2.83 | 21.04 | 0.00 | 0.00 | 4.45 | 28.32 | 51% | 27.54
3 | Bhima LIS / Kalaburgi | 23.63 | 0.00 | 0.00 | 12.74 | 5.09 | 1.94 | 19.77 | 84% | 3.86
4 | Karanja/ Kalaburagi | 11.23 | 0.00 | 0.00 | 0.00 | 4.53 | 1.85 | 6.38 | 57% | 4.85
Total |  | 113.71 | 4.24 | 31.42 | 15.24 | 13.49 | 8.24 | 72.63 | 64% | 41.08
Notes: CA PROPOSAL for Rameshwara amounting to Rs received. COMMENTS HAS BEEN GIVEN .
UTP authorities has been requested for CA proposal.

## Slide 123
Total Expenditure Progress
(TE in Rs. Crores)
7th PIRC Meeting Progress Review Presentations
Sl. No. | Project Name | Target | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | Total Financial Progress | % of Financial Progress
1 | Sri Rameshwara LIS / Belagavi | 56.31 | 8.15 | 22.14 | 8.15 | 11.26 | 4.04 | 53.74 | 95%
2 | Upper Tunga/ Shivamogga | 107.62 | 11.35 | 5.94 | 13.71 | 14.21 | 5.73 | 50.94 | 47%
3 | Bhima LIS / Kalaburgi | 56.56 | 0.00 | 10.87 | 17.91 | 11.07 | 3.58 | 43.43 | 77%
4 | Karanja/ Kalaburagi | 42.60 | 0.00 | 0.00 | 1.88 | 3.75 | 8.91 | 14.54 | 34.13%
Total |  | 263.09 | 19.50 | 38.95 | 41.65 | 40.29 | 22.26 | 162.65 | 62%

## Slide 124
Broad Review
(CCA in Th. ha.)
7th PIRC Meeting Progress Review Presentations
Sl. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03.2016 | Progress in CCA for 99 Priority Projects (including 2015-16 progress) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
 |  |  | (A) | (B) |  |  |  |  | 
1 | Sri Rameshwara LIS / Belagavi | 13.8 | 2.38 | 10.90 | 13.28 | 96% | 13.8 | 13.8 | 100%
2 | Upper Tunga/ Shivamogga | 80.494 | 55.05 | 11.01 | 66.06 | 82% | 80.49 | 72.39 | 90%
3 | Bhima LIS / Kalaburgi | 24.292 | 11.39 | 11.62 | 23.01 | 95% | 24.29 | 24.29 | 100%
4 | Karanja/** Kalaburagi | 29.227 | 22.11 | 3.36 | 25.47 | 87% | 29.23 | 26.565 | 90.87%
Total |  | 147.813 | 90.94 | 36.84 | 127.68 | 86% | 147.813 | 134.631 | 91%
Note: NLBC-ERM project is discontinued from CADWM programme of PMKSY vide letter from The Secretary , Ministry of JalShakthi Dated:15-11-2019

## Slide 125
Sl No. | Project Name | Date of Visit | Remarks (Visiting Team)
1 | Upper Tunga Project | 18th – 20th Nov. 2019 | Chief Engineer & Director (Mon)
2 | Sri Rameshwara LIS | 11th – 13th Feb. 2020 | Chief Engineer, Director (Mon) & DD (Mon)
3 | Karanja Project | 03rd – 04th Mar. 2020 | Chief Engineer, Director (App) & AD (App)
4 | Bhima LIS | 05th Mar. 2020 | Chief Engineer, Director (App) & AD (App)
7th PIRC Meeting Progress Review Presentations
Projects last visited by CWC Officers

## Slide 126
General :
Programme delayed in first and second quarter of this financial year due to COVID-19 lockdown guidelines.
Shortage of staffs in various divisions.
Farmers reluctance to pay their share in formation of Water Users Co-operative societies.
Absence of Hydraulic Connectivity up to Outlet.
State budget constraints.
U.T.P. :
Slow progress of UTP CADWM is due to slow progress of AIBP WORKS.
AIBP works of UTP are delaying due to delay in compensation for land acquisition.
Earlier railway crossing at 232 km, highway crossing at 231.942 km and halt of works due heavy rains last year delayed it.
SRLIS :
Farmers are not coming forward to form balance WUCs as they have not received land compensation. This issue needs to be resolved.
Bhima LIC
An area of 1284 ha is unviable to irrigate through FICs and the same is going to taken up under micro irrigation.
Karanja:
Karanja was included in 2018. They have shown good progress during last year, and hence will complete works this year.
7th PIRC Meeting Progress Review Presentations
Bottlenecks of Projects

## Slide 127
Glimpses Of Project Progress: Upper Tunga Project
7th PIRC Meeting Progress Review Presentations
Construction of FIC under outlet of sub minor-6 of minor-26
Construction of FIC under minor-26 of Distributory-2
Construction of FIC under Outlet of Minor-1 of DY-5

## Slide 128
Glimpses Of Project Progress: Sri Rameshwara LIS
7th PIRC Meeting Progress Review Presentations
Construction of CSD works at SRLIS

## Slide 129: 7th PIRC Meeting Progress Review Presentations
FIC works under Bhima LIS
Glimpses Of Project Progress: Bhima LIS

## Slide 130: Construction of FIC works under Karanja Project
7th PIRC Meeting Progress Review Presentations
Glimpses Of Project Progress: Karanja Project

## Slide 131
Glimpses Of Project Progress: Karanja Project
7th PIRC Meeting Progress Review Presentations
ATIWAL LIFT IRRIGATION SCEHME- NORTH CANAL RAILWAY CROSSING WORKS
TROUGH CONSTRUCTION IN D1(A) OF
KARANJA LIFT IRRIGATION

## Slide 132
Key Reasons For Progress Delays
 | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
X | Delay in Govt/Administrative clearances.-Administrative Approval for Rs747.57 cr in process of Approval
X | State budget constraints.
√ | Unwillingness of farmers.
X | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
X | Other Issue (to be specified).
7th PIRC Meeting Progress Review Presentations

## Slide 133: THANK YOU

## Slide 134
MONITORING SOUTH ORGANISATION
CENTRAL WATER COMMISSION, BENGALURU
7th Project Implementation Review Committee (PIRC) for CADWM Implementation under 99 PRIORITIZED PROJECTS- Goa State
Date -11th September,2020

## Slide 135
projects under pmksy- goa state
Tillari Project
It is a Inter-state project of Goa & Maharashtra
7th PIRC Meeting : Progress Review Presentations
 | Maharastra |  | Goa |  | 
 | Length in km | CCA in ha | Length in km | CCA in ha | No of Distributaries
LBC | 18.37 | 1671 | 37.4 | 10267 | 12 (8 Dy + 4 Minors)
RBC | 24.7 | 5005 | 23.75 | 4254 | 6
Total |  | 6676 |  | 14521 | 
CCA Created up to 6/20 -- 11830 ha
CCA Utilised up to 3/16 -- 5854 ha
Balance CCA to be utilised under PMKSY -- 8667 ha

## Slide 136
7th PIRC Meeting: Progress Review Presentations
7th PIRC Meeting Progress Review Presentations

## Slide 137
State : Goa
Number of Projects : 1 Projects Included: 1 Projects Availing CA: 1 Projects Reporting Progress: 1
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | CCA (in th. Ha.) | WUA (Nos)
Target | 215.46 | 106.28 | 46.62 | 100
Progress | 21.97 | 3.56 | 14.25 | 72
Physical Progress
State : Goa
7th PIRC Meeting Progress Review Presentations
CA
Expenditure
CCA
WUAs
23.6 %
12 %
38 %
Notes: FP -23.6% CA release- 0 % PP of CCA 12.1 % WUA – 38.2 %

## Slide 138
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (06/20) | Total | % Progress |  | 
1 | Tillari Irrigation Project | 8.667 | 0.007 | 0 | 0.752 | 0.167 | 0.122 | 1.048 | 12.09 | 4.20 | 3.42
( Area in Th. Ha.)
7th PIRC Meeting Progress Review Presentations

## Slide 139
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (6/20) | Total | % Progress |  | 
1 | Tillari Irrigation Project | 110 | 42 | 0 | 0 | 0 | 0 | 0 | 42 | 38% | 20 | 48
(WUA’s in No’s)
7th PIRC Meeting Progress Review Presentations

## Slide 140
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (06/20) | Total | % Progress |  | 
1. | Tillari Irrigation Project | 18.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.78 | 5.73
(CA in Rs. Crores)
7th PIRC Meeting: Progress Review Presentations
Administrative approval for RCE of CADWM works is obtained on 5/2019
Proposal of CA during 2019-20 was forwarded to CADWM wing for Rs 4 Cr
Proposal of CA in this financial year also was forwarded on 20.08.20 recommending for Rs 2.66 Cr towards first instalment. (Budget 40 cr and Estimated Cost – 98 Cr)

## Slide 141
WUCS – Registered, Handed over, OTFG and Infrastructure Grant details
7th PIRC Meeting Progress Review Presentations
SL.No. | Activity | Unit | Tillari Irrigation Project CADA Works | 
1 | 2 | 3 | Target | Progress
 |  |  | 4 | 5
1 | Formation of WUCS (Registration) | No’s | 110 | 42
2 | Handed over (MoU) | No’s | 42 | 10
3 | One time Fuctional Grant (OTFG ) to WUCS | Ha | 5085 | 0
 |  | Fin (lakhs) | 27.46 | 0
4 | Infrastructure grant to WUCS | No’s | 42 | 0
 |  | Fin (lakhs) | 126 | 0

## Slide 142
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (06/20) | Total | % Progress |  | 
1 | Tillari Irrigation Project | 153.65 | 4.72 | 7.16 | 9.09 | 14.16 | 1.11 | 36.24 | 23.58 | 40.00 | 77.41
(TE in Rs. Crores)
7th PIRC Meeting Progress Review Presentations

## Slide 143
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA Utilized before 31.03. 2016 (A) | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA utilized (A+B) | % CCA Progress | CCA (UlP) | Potential Created | % IPC
1 | Tillari Irrigation Project | 14.521 | 5.854 | 1.048 | 6.902 | 47.53 | 14.521 (21.056) | 11.830 (17.154) | 81.47%
(CCA in Th. ha.)
7th PIRC Meeting Progress Review Presentations

## Slide 144
Bottlenecks
Land acquisition: Farmers in various parts of command area are reluctant to practice agriculture /irrigation due to availability of better livelihood opportunities in the state of Goa.
To offset the land acquisition problems, hurdles due to Change in land use such as settlements and to avoid deep cutting etc. the original alignment of distributaries has been modified to be taken along the public road
7th PIRC Meeting Progress Review Presentations

## Slide 145
Glimpses of FICs work
FICs at Siolim Distributary near off take point of Camurlim Branch
CONSTRUCTION OF FIC IN LBMC.
7th PIRC Meeting Progress Review Presentations

## Slide 146
THANK YOU
7th PIRC Meeting Progress Review Presentations

## Slide 147
Rajasthan
Number of Projects : 2 Projects Included: 2 Projects Availing CA: 2 Projects Reporting Progress:2
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | CCA (in th. Ha.) | WUA (Nos)
Target | 450.88 | 230 | 116.586 | 36
Progress | 61.77 | 37 | 24.003 | 36
Physical Progress
6 th PIRC Meeting (Chandigarh, 28 th February 2020): Progress Review Presentations

## Slide 148
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 |  | 2017-18 | 2018-19 | 2019-20 | 2020-21 (up to Aug. 2020 | Total | % Progress | 
1 | Narmada Canal | ONLY NON –STRUCTURAL INTERVENTION SANCTIONED. |  |  |  |  |  |  |  |  | 
2 | Mod. of Gang Canal | 117.975 |  | 8.252 | 7.224 | 7.078 | 5.345 | 2.833 | 30.732 | 26.050 | 32.00
 | TOTAL | 117.975 |  | 8.252 | 7.224 | 7.078 | 5.345 | 2.833 | 30.732 | 26.050 | 32.00
( Area in Th. Ha.)
6 th PIRC Meeting (Chandigarh, 28 th February 2020): Progress Review Presentations

## Slide 149: MICRO-IRRIGATION COMPONENT Progress
Sr. No. | Project | Balance CCA Target (In Th Ha) | CCA Progress (In Th Ha) |  |  |  |  |  |  | Target for 2020-21 (In Th Ha)
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (up to Aug. 2020) | Total | % Progress | 
1 | Narmada Canal | The micro irrigation system has already been installed in the 2,46,000 Ha. command area of the Narmada Canal Project in Rajasthan prior to sanction of CADWM. |  |  |  |  |  |  |  | 
2 | Mod. of Gang Canal | The Micro-Irrigation in Gang Canal Project Phase-II exempted by DoWR, GoI vide letter No. N-19011/04/2015-(CAD)/Vol.II/791-93 dated 26.08.2019 and this area included in project for OFD works. |  |  |  |  |  |  |  | 
 | TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 150
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  |  |  |  |  | Target for 2020-21
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (up to Aug. 2020) | Total | % Progress | System Handed Over to WUA | One Time Functional Grant released | 
1 | Narmada Canal | 2231 | 2144 | 56 | 1 | 14 | 2 | 12 | 2229 | 99.91 | 2005 | 0 | 2
2 | Mod. of Gang Canal | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 180 | 100 | 180 | 0 | 0
 | TOTAL | 2411 | 2324 | 56 | 1 | 14 | 2 | 12 | 2409 | 99.92 | 2185 | 0 | 2
(WUA’s in No’s)
6 th PIRC Meeting (Chandigarh, 28 th February 2020): Progress Review Presentations

## Slide 151
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (up to Aug. 2020) | Total | % Progress | 
1 | Narmada Canal | 54.06 | 0.00 | 0.00 | 0.00 | 0.00 | 7.02 | 0.00 | 7.02 | 12.99 | 9.51
2 | Mod. of Gang Canal | 175.99 | 10.00 | 0.00 | 2.479 | 7.430 | 10.22 | 0.00 | 30.129 | 17.12 | 24.87
 | TOTAL | 230.05 | 10.00 | 0.00 | 2.479 | 7.439 | 17.24 | 0.00 | 37.149 | 16.15 | 34.38
(CA in Rs. Crores)
6 th PIRC Meeting (Chandigarh, 28 th February2020): Progress Review Presentations

## Slide 152
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 (up to Aug. 2020 | Total | % Progress | 
1 | Narmada Canal | 97.48 | 0.00 | 0.00 | 0.00 | 0.15 | 0.00 | 0.15 | 0.154 | 28.15
2 | Mod. of Gang Canal | 353.40 | 11.76 | 12.99 | 14.85 | 28.70 | 6.88 | 75.18 | 21.273 | 49.87
 | TOTAL | 450.88 | 11.76 | 12.99 | 14.85 | 28.85 | 6.88 | 75.33 | 16.707 | 78.02
(TE in Rs. Crores)
6 th PIRC Meeting (Chandigarh, 28 th February 2020): Progress Review Presentations

## Slide 153
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Narmada Canal | 246.000 | 245.610 | 0.390 | 246.000 | 100.00 | 246.00 | 246.00 | 100.00
2 | Mod. of Gang Canal | 117.975 | 1.389 | 29.343 | 30.732 | 26.05 | 96.51 | 96.51 | 100.00
 | TOTAL | 363.975 | 246.999 | 29.733 | 276.732 | 76.030 | 342.51 | 342.51 | 100.00
(CCA in Th. ha.)
6 th PIRC Meeting (Chandigarh, 28 th February 2020): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before inclusion in 99 Priority project programme.

## Slide 154
Glimpses Of Project Progress
Water course at Chak No. 69 RB Of Gang Canal Project Phase-II
6 th PIRC Meeting (Chandigarh, 28 th February 2020): Progress Review Presentations
{.....Project Photographs (4/5) may be provided}

## Slide 155
Glimpses Of Project Progress
Water course at Chak No 73 NP of Gang Canal Project Phase-II
6 th PIRC Meeting (Chandigarh, 28 th February 2020): Progress Review Presentations
{.....Project Photographs (4/5) may be provided}

## Slide 156
Glimpses Of Project Progress
Sprinkler system at Jaisala Distributary of Narmada Canal Project
6 th PIRC Meeting (Chandigarh, 28 th February 2020): Progress Review Presentations
{.....Project Photographs (4/5) may be provided}

## Slide 157
Key Reasons For Progress Delays
Status | Key Reason
X | Absence of Hydraulic Connectivity up to Outlet.
X | Delay in Govt/Administrative clearances.
√ | State budget constraints.
X | Delays in tendering.
√ | Delay in release of CA . In FY 2019-20 the 1st instalment of CA was received in December 2019. Due to which the progress was hampered.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
√ | Additional CCA of 73100 Ha added into GCP-II on 31.12.2019 only.
6 th PIRC Meeting (Chandigarh, 28 th February 2020): Progress Review Presentations

## Slide 158
6 th PIRC Meeting (Chandigarh, 28 th February 2020): Progress Review Presentations
Issues for CAD Narmada Canal Project:
1. Central Assistance:
a. Narmada Canal Project
The Central Assistance of Rs. 7.02 Crore for FY 2019-2020 was sanctioned by DoWR, GoI on 24.12.2019 but the amount has been deposited in the State Government’s account on dated 13.05.2020.
b. Gang Canal Project Phase-II
The proposals for release of 1st instalment of CA for FY 2020-21 amounting to Rs.14.95 Crs. Submitted to MoJS New Delhi through CWC Jaipur on 01.09.2020. Early release of CA is requested .
The MoU extension up to 31.03.22 have been submitted to MoJS New Delhi through CWC Jaipur on 01.09.2020.
The Concurrence of GoI for State Share portion under LTIF is to be given by DoWR, MoJS early action is requested.
Extra Slides

## Slide 159
THANKS………
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 160: 7th PIRC Meeting (11th September, 2020) : Progress Review Presentations
Chart: 
| Total Expenditure (Rs.Crore) | CA (Rs.Crore) | Balance CCA (in th.Ha) | WUA (Nos)
Target | 122.71 | 63.65 | 22.04 | 74
Progress | 35.16 | 17.58 | 8.661 | 68
MANIPUR
Financial Progress
Physical Progress
122.71
35.16
17.58
63.65
8.661
68
74
22.04
Number of Projects :2 Projects Included : 2
Projects Availing CA : 2 Projects Reporting Progress : 2
MANIPUR

## Slide 161: 7th PIRC Meeting (11th September, 2020) : Progress Review Presentations
Sl. No | Project | Project Total CCA | CCA Progress |  |  |  |  | Target for 2020-21
 |  |  | 2017-18 | 2018-19 | 2019-20 | Total CCA Progress | % of CCA Progress | 
1 | Dolaithabi Barrage | 5.500 | 1.314 | 0 | 1.042 | 2.356 | 42% | 3.144
2 | Thoubal | 16.536 | 3.716 | 0 | 2.589 | 6.305 | 38% | 10.231
 | Total | 22.036 | 5.030 | 0 | 3.631 | 8.661 | 39% | 13.375
Manipur Yearwise CCA Progress
(Area in Th. Hectare)
MANIPUR

## Slide 162: 7th PIRC Meeting (11th September, 2020) : Progress Review Presentations
Sl. No | Project | Physical Target (Th. Ha.) | Financial Target (Rs. In lakhs) | Progress 2016-2020 | Target for 2020-2021 (Th. Ha.)
1 | Dolaithabi Barrage | 0.55 | 275.00 | 0 | 0.55
2 | Thoubal | 1.654 | 827.00 | 0 | 1.654
 | Total | 2.204 | 1102.00 | 0 | 2.204
M.I. TARGET
MANIPUR
* All the command areas of the two projects are under paddy cultivation during kharif, as such harvest will be completed by end of November, 2020. It is proposed to start M.I. Works in December, 2020 and targeted to complete 25% of total area, another 25% in January, 2021 and remaining 50% during February and March, 2021.

## Slide 163: 7th PIRC Meeting (11th September, 2020) : Progress Review Presentations
Sl. | Project | WUA Target | WUA Progress |  |  |  |  | 
 |  |  | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress
1 | Dolaithabi Barrage | 19 | 11 | 2 | 0 | 0 | 13 | 68%
2 | Thoubal | 55 | 18 | 3 | 0 | 34 | 55 | 100%
 | Total | 74 | 29 | 5 | 0 | 34 | 68 | 91%
Manipur Yearwise WUA Progress
(WUA in No.)
MANIPUR
PIM Act has not been enacted in the State. Therefore, WUAs formed are being registered under the Manipur Societies Registration Act 1989. 64 Nos. Of WUAs has been registered and all remaining are under process with the Registrar of Societies, Government of Manipur.

## Slide 164: 7th PIRC Meeting (11th September, 2020) : Progress Review Presentations
Sl | Project | Overall CA Target | CA Release Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | Total | % Progress | 
1 | Dolaithabi Barrage | 15.887 | 4.462 | 0 | 0 | 0 | 0 | 4.462 | 28% | 11.425
2 | Thoubal | 47.768 | 13.118 | 0 | 0 | 0 | 0 | 13.118 | 27.5 % | 34.650
 | Total | 63.655 | 17.58 | 0 | 0 | 0 | 0 | 17.58 | 27.6% | 46.075
Manipur Yearwise CA Release Progress
(CA in Rs. Crores)
MANIPUR
* Central Assistance was not proposed during 2016-17 to 2019-20 as state could not provide state matching share. The CA released in 2015-16 was utilised in 2017-18. Loan has been sanctioned to meet state share from LTIF NABARD in December, 2019.

## Slide 165: 7th PIRC Meeting (11th September, 2020) : Progress Review Presentations
Sl. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2020-21
 |  |  | 2017-18 | 2018-19 | 2019-20 | Total | % Progress | 
1 | Dolaithabi Barrage | 30.627 | 5.050 | 0 | 4.010 | 9.060 | 29% | 21.567
2 | Thoubal | 92.085 | 14.290 | 0 | 11.810 | 26.100 | 28% | 65.985
 | Total | 122.712 | 19.340 | 0 | 15.820 | 35.160 | 28% | 87.552
Total Expenditure Progress
(TE in Rs. Crores)
MANIPUR

## Slide 166: -THANKS-

## Slide 167
ASSAM
Number of Projects : 3 Projects Included: 3 Projects Availing CA: 3 Projects Reporting Progress:3
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | Balance CCA (in th. Ha.) | WUA (Nos)
Target | 215.458 | 96.634 | 496.87 | 127
Progress | 8.429 | 3.55 | 10.581 | 69
Physical Progress
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations
ASSAM

## Slide 168
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
1 | Champamati | 6.587 | 0 | 1.191 | 1.817+ 1.347(MI) | 0 | 2.07+ 0.162(MI) | 6.587 | 100% | 0.00
2. | Dhansiri Irrigation Project | 31.115 | 0 | 0 | 9.758+ 0.140(MI) | 6.051+ 0.860(MI) | 0 | 16.809 | 54% | 14.306
3. | Borolia | 8.917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.917
 | TOTAL | 46.619 | 0 | 1.191 | 13.062 | 6.911 | 2.232 | 23.396 | 60.06 | 25.455
( Area in Th. Ha.)
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations

## Slide 169
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  |  |  | Target for 2020-21
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
1 | Champamati | 40 | 0 | 20 | 05 | 0 | 2 | 0 | 27 | 67.5% | 13
2. | Dhansiri Irrigation Project | 50 | 44 | 0 | 0 | 0 | 0 | 0 | 44 | 88% | 6
3. | Borolia | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 30% | 7
 | TOTAL | 100 | 47 | 20 | 05 | 0 | 2 | 0 | 74 | 62.83% | 26
(WUA’s in No’s)
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations

## Slide 170
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
1 | Champamati | 13.715 | 0 | 0 | 3.550 | 0 | 4.0 | 10.765* | 78.49% | 2.95
2. | Dhansiri Irrigation Project | 76.0364 | 9.73 | 0 | 0 | 0 | 0 | 9.73 | 12.80% | 66.3064
3. | Borolia | 16.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.00
 | TOTAL | 106.2714 | 9.73 | 0 | 3.550 | 0 | 0 | 20.495 | 19.3 | 
(CA in Rs. Crores)
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations
* Includes release of Rs.3.215 Cr. during FY 2015-16

## Slide 171
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  |  |  | Target for 2020-21
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
1 | Champamati | 27.23 | 0 | 6.43 | 7.10 | 0 | 8.00 | 21.53 | 79.07 | 5.70
2. | Dhansiri Irrigation Project | 151.99 | 0 | 2.333 | 6.096 | 9.640 | 0 | 18.069 | 11.89 | 133.921
3. | Borolia | 36.2381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.60
 | TOTAL | 215.458 | 0 | 8.763 | 13.196 | 5.889 | 8 | 39.599 | 18.4 | 161.221
(TE in Rs. Crores)
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations

## Slide 172
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Champamati | 6.587 | 0 | 6.587 | 6.587 | 100 | 23.504 | 23.504 | 100
2. | Dhansiri Irrigation Project | 38.615 | 7.500 | 16.809 | 24.309 | 54 | 77.23 | 55.26 | 71.55
3. | Borolia | 8.917 | 0 | 0 | 0 | 0 | 13.56 | 3.3 | 24.34
 | TOTAL | 54.119 | 7.500 | 21.164 | 28.664 | 154 | 114.294 | 82.064 | 71.8
(CCA in Th. ha.)
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 173
MI PROGRESS
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations
Sr. No. | State | CCA Target (Th. Ha.) | CCA Progress | 
 |  |  | Created (Th. Ha.) | % of Progress
1 | Champamati | 1.509 | 1.509 | 100
2 | Dhansiri Irrigation Project | 3.861 | 1 | 25.9
3 | Borolia | 0.972 | 0 | 0
 | TOTAL | 6.342 | 2.509 | 39.56

## Slide 174: PROJECT IN BRIEF (Champamati Irrigation Project)
The Champamati Irrigation Project is a Major Irrigation Project envisages construction of Barrage and canal system to irrigate 24994Ha (revised to 23504Ha due to change of land used pattern) The Physical overall progress is 100%
Irrigation Potential created till 31/08/2020is 23504Ha (100%).
Irrigation Potential Utilized till 31/08/2020 is 23504Ha. (100%)
Estimated Cost of CADWM is Rs.27.23Cr.
Total cost of the project under AIBP is 213.510 Cr.
WUA details in no. (target/formed/registered/balance) : 40/ 27 /13
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations

## Slide 175
Glimpses Of Project Progress
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations
PROJECT IN BRIEF (Dhansiri)
Dhansiri Irrigation Project (Major), in Udalguri District (BTAD), Assam was initiated in the year 1975 across the river Dhansiri at Bhairabkunda near Tri-Junction of Assam, Arunachal and Bhutan.
Targeted Potential AIA = 77230 Ha.
CCA = 38615 Ha.
Intensity of Irrigation = 200%
Up to date Potential Created = 55258 Ha. (71.5 %)
Potential Utilized = 21800 Ha. (28.23%)
Balance Potential to be Created = 21972 Ha. (28.45%)

## Slide 176: PROJECT IN BRIEF (Borolia Irrigation Project)
The Borolia Irrigation Project is a Medium Irrigation Project envisages construction of barrage and canal system to irrigate 9717Ha CCA/ 13562Ha. UIP. The Physical overall progress is 51%
Irrigation Potential created till 31/08/2020 is 3300Ha (24%).
Irrigation Potential Utilized till 31/08/2020 is 1750Ha. (18 %)
Estimated Cost of CADWM is Rs.36.24Cr. (CS-16.52 + SS 19.72)
WUA details in no. (target/formed/registered/balance) : 10/ 3 /3 /7
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations

## Slide 177
Head Works of Dhansiri Irrigation Project (MAJOR)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
{.....Project Photographs (4/5) may be provided}
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations

## Slide 178
Brick Lined Field Channel
{.....Project Photographs (4/5) may be provided}
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations

## Slide 179
Brick Lined Field Channel
{.....Project Photographs (4/5) may be provided}
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations

## Slide 180
Brick Lined Field Channel
{.....Project Photographs (4/5) may be provided}
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations

## Slide 181
Brick Lined Field Channel
{.....Project Photographs (4/5) may be provided}
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations

## Slide 182
MDTW SCHEME ( 7.5 H.P.) WITH SOLAR POWER
{.....Project Photographs (4/5) may be provided}
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations

## Slide 183
STW WITH DIESEL PUMP SET UNDER MICRO IRRIGATION
{.....Project Photographs (4/5) may be provided}
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations

## Slide 184
OFFICE ROOM FOR WATER USERS ASSOCIATION
{.....Project Photographs (4/5) may be provided}
7th PIRC Meeting (11th September/ 2020) Progress Review Presentations

## Slide 185
Glimpses Of Project Progress (Champamati Irrigation Porject)

## Slide 186
Glimpses Of Project Progress
WATER SUPPLY IN LEFT BANK MAIN CANAL

## Slide 187
Glimpses Of Project Progress
WATER SUPPLY IN RIGHT BANK MAIN CANAL

## Slide 188: Field channel at ch 300 m of LBC-3,CIP,BTC,ASSAM
Glimpses Of Project Progress

## Slide 189: Field channel at ch 860 m of LBC-6,CIP,BTC,ASSAM
Glimpses Of Project Progress

## Slide 190: Field channel at ch1000mof RBC-3,CIP,BTC,ASSAM
Glimpses Of Project Progress

## Slide 191
Glimpses Of Project Progress (Borolia Irrigation Project)

## Slide 192
Glimpses Of Project Progress

## Slide 193
WATER SUPPLY IN BRANCH CANAL B-4
Glimpses Of Project Progress

## Slide 194
WATER SUPPLY IN BRANCH CANAL B-7
Glimpses Of Project Progress

## Slide 195: -THANKS-

## Slide 196: 7th Meeting of Project Implementation Review Committee (PIRC) 11.09.2020
Monitoring & Appraisal Directorate (TS),
KGBO, CWC, Hyderabad
CADWM Implementation in Telangana State

## Slide 197
TELANGANA
Number of Projects : 11 Projects Included: 11 Projects Availing CA: 9 Projects Reporting Progress:1
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | Balance CCA (in th. Ha.) | WUA (Nos)
Target | 1460.73 | 702.95 | 529.028 | 1148
Progress | 0 | 0 | 0 | 1
Physical Progress
7th PIRC Meeting (11th Sep 2020): Progress Review Presentations

## Slide 198
CCA Progress
Sr. No. | Project | Balance CCA Target in Th. Ha | CCA Progress |  |  |  |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress |  | 
1 | J. Chokha Rao LIS | 248.685 | 0 | 0 | 10.679 | 0 | 10.679 | 4.29 | 141.776 | 96.23
2. | Gollavagu Project | 3.845 | 0 | 0 | 0 | 0 | 0 | 0 | 1.922 | 1.922
3. | Mathadivagu Project | 3.44 | 0 | 0 | 0 | 0 | 0 | 0 | 1.72 | 1.72
4. | Palemvagu project | 2.014 | 0 | 0 | 0 | 0 | 0 | 0 | 1.007 | 1.007
5. | Peddavagu @ Jagannathpur | 6.073 | 0 | 0 | 0 | 0 | 0 | 0 | 0.303 | 0.304
6. | Peddavagu @ Neelwai | 5.26 | 0 | 0 | 0 | 0 | 0 | 0 | 2.630 | 2.630
7. | Rajiv Bheema L.I. Scheme | 82.153 | 0 | 0 | 0 | 0 | 0 | 0 | 30.00 | 52.153
8. | Rallivagu project | 0.918 | 0 | 0 | 0 | 0 | 0 | 0 | 0.459 | 0.459
9. | SriKomaram Bheem | 9.915 | 0 | 0 | 0 | 0 | 0 | 0 | 4.957 | 4.957
10. | SRSP St.II | 73.138 | 0 | 0 | 0 | 0 | 0 | 0 | 31.411 | 41.727
11. | Indiramma Flood Flow Canal | 93.587 | 0 | 0 | 0 | 0 | 0 | 0 | 20.24 | 65.253
 | Total | 529.028 | 0 | 0 | 10.679 |  | 10.679 | 4.29 | 236.425 | 268.362
7th PIRC Meeting (11th Sep 2020): Progress Review Presentations

## Slide 199
Micro Irrigation Progress
Sr. No. | Project | Micro Irrigation Target in Th. Ha | MI Progress |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | 2020-21 | Total | % Progress |  | 
1 | J. Chokha Rao LIS | 55.382 | 0 | 0 | 0 | 28.739 | 26.642
2. | Gollavagu Project | 0.384 | 0 | 0 | 0 | 0.192 | 0.192
3. | Mathadivagu Project | 0.345 | 0 | 0 | 0 | 0.17 | 0.175
4. | Palemvagu project | 0.202 | 0 | 0 | 0 | 0 | 0.202
5. | Peddavagu @ Jagannathpur | 0.607 | 0 | 0 | 0 | 0.303 | 0.304
6. | Peddavagu @ Neelwai | 0.526 | 0 | 0 | 0 | 0.263 | 0.263
7. | Rajiv Bheema L.I. Scheme | - | - | - | - | - | -
8. | Rallivagu project | 0.918 | 0 | 0 | 0 | 0.459 | 0.459
9. | SriKomaram Bheem | 0.991 | 0 | 0 | 0 | 0.495 | 0.496
10. | SRSP St.II | 1.269 | 0 | 0 | 0 | 0 | 1.269
11. | Indiramma Flood Flow Canal | 9.359 | 0 | 0 | 0 | 0 | 9.359
 | Total | 69.983 | 0 | 0 | 0 | 30.621 | 39.361
7th PIRC Meeting (11th Sep 2020): Progress Review Presentations

## Slide 200
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  | No. of WUA registered | Target for 2020-21 | Target for 2021-22
 |  |  | Before April 2016 | WUAs Status |  |  | 
1 | J. Chokha Rao LIS | 498 | 0 | WUAs shall be formed after completion of the AIBP projects. | 0 | 0 | 498
2. | Gollavagu Project | 8 | 0 |  | 0 | 4 | 4
3. | Mathadivagu Project | 7 | 0 |  | 0 | 3 | 4
4. | Palemvagu project | 8 | 0 |  | 0 | 0 | 8
5. | Peddavagu @ Jagannathpur | 15 | 0 |  | 0 | 6 | 9
6. | Peddavagu @ Neelwai | 11 | 0 |  | 0 | 4 | 7
7. | Rajiv Bheema L.I. Scheme | 164 | 0 |  | 0 | 0 | 164
8. | Rallivagu project | 3 | 0 |  | 0 | 1 | 2
9. | SriKomaram Bheem | 20 | 0 |  | 0 | 10 | 10
10. | SRSP St.II | 356 | 0 |  | 0 | 0 | 356
11. | Indiramma Flood Flow Canal | 58 | 0 |  | 0 | 4 | 54
 | Total | 1148 | 0 |  | 0 | 32 | 1116
(WUA’s in No’s)
7th PIRC Meeting (11th Sep 2020): Progress Review Presentations

## Slide 201
Functional Grant
Sr. No. | Project | Target | Grant Given | Grant Handed Over
1 | J. Chokha Rao LIS | 248.685 | 0 | 0
2. | Gollavagu Project | 3.845 | 0 | 0
3. | Mathadivagu Project | 3.440 | 0 | 0
4. | Palemvagu project | 4.100 | 0 | 0
5. | Peddavagu @ Jagannathpur | 0 | 0 | 0
6. | Peddavagu @ Neelwai | 5.260 | 0 | 0
7. | Rajiv Bheema L.I. Scheme | 82.153 | 0 | 0
8. | Rallivagu project | 0.917 | 0 | 0
9. | SriKomaram Bheem | 9.915 | 0 | 0
10. | SRSP St.II | 178.066 | 0 | 0
11. | Indiramma Flood Flow Canal | 93.587 | 0 | 0
 | Total | 629.968 | 0 | 0
(Target in Th.Ha)
7th PIRC Meeting (11th Sep 2020): Progress Review Presentations

## Slide 202
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | 2017-18 | 2018-19 | 2019-20 | Total | % Progress |  | 
1 | J. Chokha Rao LIS | 380.351 | 10.22 | 0 | 0 | 10.22 | 2.69 | 160.25 | 209.88
2. | Gollavagu Project | 7.186 | 0 | 1.03 | 0 | 1.03 | 14.33 | 3.078 | 3.078
3. | Mathadivagu Project | 6.187 | 0 | 1.8 | 0 | 1.8 | 29.09 | 2.1935 | 2.1935
4. | Palemvagu project | 2.601 | 0 | 0.5152 | 0 | 0.5152 | 19.60 | 0.35 | 1.7358
5. | Peddavagu @ Jagannathpur | 12.203 | 0 | 0 | 0 | 0 | 0.00 | 6.10 | 6.103
6. | Peddavagu @ Neelwai | 6.669 | 0 | 1.99 | 0 | 1.99 | 29.84 | 2.34 | 2.339
7. | Rajiv Bheema L.I. Scheme | 122.224 | 0 | 0 | 0 | 0 | 0.00 | 70.52 | 51.704
8. | Rallivagu project | 1.472 | 0 | 0.28 | 0 | 0.28 | 19.02 | 0.596 | 0.596
9. | SriKomaram Bheem | 19.096 | 0 | 5.89 | 0 | 5.89 | 29.69 | 6.603 | 6.603
10. | SRSP St.II | 103.241 | 0 | 11.56 | 0 | 11.56 | 11.19 | 45.45 | 46.231
11. | Indiramma Flood Flow Canal | 48.261 | 0 | 3.06 | 0 | 3.06 | 6.34 | 2.05 | 43.151
 | Total | 709.491 | 10.22 | 26.125 | 0 | 36.352 |  | 299.531 | 373.614
(CA in Rs. Crores)
7th PIRC Meeting (11th Sep 2020): Progress Review Presentations

## Slide 203
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress |  | 
1 | J. Chokha Rao LIS | 759.948 | Inclusion on 31st March, 2017 | 0 | 0 | 5.22 | 0 | 5.22 | 0.686 | 340.220 | 419.728
2. | Gollavagu Project | 20.400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8.160 | 12.240
3. | Mathadivagu Project | 12.635 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6.300 | 6.335
4. | Palemvagu project | 5.200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.718 | 3.482
5. | Peddavagu @ Jagannathpur | 52.550 |  | 0 | 0 | 0 | 0 | 0 | 0 | 26.275 | 26.275
6. | Peddavagu @ Neelwai | 25.121 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10.675 | 14.446
7. | Rajiv Bheema L.I. Scheme | 245.270 |  | 0 | 0 | 0 | 0 | 0 | 0 | 150.780 | 94.490
8. | Rallivagu project | 5.570 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2.180 | 3.390
9. | SriKomaram Bheem | 60.222 |  | 0 | 0 | 0 | 0 | 0 | 0 | 24.089 | 36.133
10. | SRSP St.II | 204.080 |  | 0 | 0 | 0 | 0 | 0 | 0 | 71.400 | 132.680
11. | Indiramma Flood Flow Canal | 97.239 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9.396 | 87.843
 | Total | 1488.235 |  | 0 | 0 | 5.22 | 0 | 5.22 |  | 651.192 | 837.042
(TE in Rs. Crores)
7th PIRC Meeting (11th Sep 2020): Progress Review Presentations

## Slide 204
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | J. Chokha Rao LIS | 248.685 | 0 | 10.679 | 10.679 | 4.29 | 248.685 | 115.485 | 46.44
2. | Gollavagu Project | 3.845 | 0 | 0 | 0 | 0 | 3.845 | 3.845 | 100
3. | Mathadivagu Project | 3.44 | 0 | 0 | 0 | 0 | 3.440 | 3.440 | 100
4. | Palemvagu project | 2.014 | 0 | 0 | 0 | 0 | 4.100 | 3.035 | 74.02
5. | Peddavagu @ Jagannathpur | 6.073 | 0 | 0 | 0 | 0 | 6.073 | 0 | 0
6. | Peddavagu @ Neelwai | 5.26 | 0 | 0 | 0 | 0 | 5.260 | 3.237 | 61
7. | Rajiv Bheema L.I. Scheme | 82.153 | 0 | 0 | 0 | 0 | 82.153 | 59.818 | 72.81
8. | Rallivagu project | 0.918 | 0 | 0 | 0 | 0 | 0.918 | 0.918 | 100
9. | SriKomaram Bheem | 9.915 | 0 | 0 | 0 | 0 | 9.915 | 6.475 | 65.0
10. | SRSP St.II | 73.138 | 0 | 0 | 0 | 0 | 178.066 | 142.815 | 80.20
11. | Indiramma Flood Flow Canal | 93.587 | 0 | 0 | 0 | 0 | 93.587 | 2.954 | 3.16
 | Total | 529.028 | 0 | 10.679 | 10.679 |  | 636.042 | 342.022 | 
(CCA in Th. ha.)
7th PIRC Meeting (11th Sep 2020): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 205
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
√ | Delay in Govt/Administrative clearances.
X | State budget constraints.
X | Unwillingness of farmers.
X | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
√ | Other Issue (to be specified). Due to election process progress is hampered.
7th PIRC Meeting (11th Sep 2020): Progress Review Presentations

## Slide 206
UIP, IPC, IPU for AIBP
Sr. No. | Project | CADWM | AIBP |  | 
 |  | Total CCA of Project | Ultimate Irrigation Potential | Potential Created | Potential Utilized (2019-20)
1 | J. Chokha Rao LIS | 248.685 | 248.685 | 115.485 | 48.00
2. | Gollavagu Project | 3.845 | 3.845 | 3.845 | 6.139
3. | Mathadivagu Project | 3.44 | 3.440 | 3.44 | 6.070
4. | Palemvagu project | 2.014 | 4.100 | 3.035 | 2.382
5. | Peddavagu @ Jagannathpur | 6.073 | 6.073 | 0.00 | 0.00
6. | Peddavagu @ Neelwai | 5.26 | 5.260 | 3.237 | 3.237
7. | Rajiv Bheema L.I. Scheme | 82.153 | 82.153 | 59.818 | 59.818
8. | Rallivagu project | 0.918 | 0.918 | 0.918 | 1.549
9. | SriKomaram Bheem | 9.915 | 9.915 | 6.475 | 6.094
10. | SRSP St.II | 73.138 | 178.066 | 142.815 | 101.00
11. | Indiramma Flood Flow Canal | 93.587 | 93.587 | 2.954 | 2.954
 | Total | 529.028 | 636.042 | 342.022 | 237.243
(in Th. ha.)
6th PIRC Meeting (Chandigarh, 28th Feb 2020): Progress Review Presentations

## Slide 207: Thank You

## Slide 208
Andhra Pradesh
Number of Projects : 7 Projects Included: 7 Projects Availing CA: 7 Projects Reporting Progress:0
7th PIRC Meeting (11th September 2020):
Progress Review Presentations
Chart: Financial Progress
| Total Expenditure (Rs. Crore) | CA (Rs.Crore) | Balance CCA in Th. Ha | WUA (Nos)
Target | 971.4 | 349.37 | 179 | 418
Progress | 0.92 | 69.18 | 0 | 51

## Slide 209
CCA Progress
( Area in Th. Ha.)
7th PIRC Meeting (11th September 2020):
Progress Review Presentations
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  |  |  | Target for 2021-22
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
1 | Gundalkamma | 32.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.38
2 | Musurumilli | 5.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.90
3 | Pushkara LIS | 46.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.72
4 | Tadipudi LIS | 54.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.87
5 | Taraka Thirtha Sagaram Reservoir | 4.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - (Works will be taken up after completion of Distributory System)
6 | Thotapali Barrage Project | 29.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.23
7 | Yerracalva | 5.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.90
 | TOTAL | 178.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115.00

## Slide 210
WUA Progress
(WUA’s in No’s)
7th PIRC Meeting (11th September 2020):
Progress Review Presentations
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  |  |  | Target for 2021-22
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
1 | Gundalkamma | 40 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 100 | 0
2 | Musurumilli | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Pushkara LIS | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Tadipudi LIS | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48
5 | Taraka Thirtha Sagaram Reservoir | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - (Works will be taken up after completion of Distributory System)
6 | Thotapali Barrage Project | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53
7 | Yerracalva | 11 | 5 | 0 | 0 | 0 | 0 | 6 | 11 | 100 | 0
 | TOTAL | 418 | 5 | 0 | 0 | 0 | 0 | 46 | 51 | 12 | 101

## Slide 211
CA Release Progress
(CA in Rs. Crores)
7th PIRC Meeting (11th September 2020):
Progress Review Presentations
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  |  |  | Target for 2021-22
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
1 | Gundalkamma | 47.15 | 0 | 0 | 3.64 | 0 | 0 | 3.64 | 7.72 | 28.72
2 | Musurumilli | 12.68 | 0 | 0 | 4.49 | 0 | 0 | 4.49 | 35.41 | 5.40
3 | Pushkara LIS | 99.66 | 0 | 0 | 35.85 | 0 | 0 | 35.85 | 35.97 | 42.11
4 | Tadipudi LIS | 109.34 | 0 | 0 | 16.4 | 0 | 0 | 16.4 | 15 | 61.34
5 | Taraka Thirtha Sagaram Reservoir | 10.14 | 0 | 0 | 0.61 | 0 | 0 | 0.61 | 6.01 | - (Works will be taken up after completion of Distributory System)
6 | Sardar Gouthu Lachanna Thotapali Barrage Project | 58.53 | 0 | 0 | 6.37 | 0 | 0 | 6.37 | 10.88 | 34.42
7 | Yerracalva | 11.87 | 0 | 0 | 1.82 | 0 | 0 | 1.82 | 15.33 | 6.63
 | TOTAL | 349.37 | 0 | 0 | 69.18 | 0 | 0 | 69.18 | 19.8 | 178.62

## Slide 212
Total Expenditure Progress
(TE in Rs. Crores)
7th PIRC Meeting (11th September 2020):
Progress Review Presentations
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  |  |  | Target for 2021-22
 |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress | 
1 | Gundalkamma | 102.7980 | 0 | 0 | 0 | 0.32 | 0.10 | 0.42 | 0.45 | 61.70
2 | Musurumilli | 31.7526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.85
3 | Pushkara LIS | 240.8701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131.54
4 | Tadipudi LIS | 277.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.33
5 | Taraka Thirtha Sagaram Reservoir | 25.9170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - (Works will be taken up after completion of Distributory System)
6 | Thotapali Barrage Project | 265.8419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.26
7 | Yerracalva | 26.5400 | 0 | 0 | 0 | 0.19 | 0.31 | 0.50 | 1.88 | 17.19
 | TOTAL | 971.4224 | 0 | 0 | 0 | 0.51 | 0.41 | 0.92 | 0.13 | 447.87

## Slide 213
Broad Review
Sr. No. | Project | CADWM |  |  |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress
1 | Gundalkamma | 32.400 | 0 | 0 | 0 | 0
2. | Musurumilli | 9.164 | 3.249 | 0 | 3.249 | 35.45
3. | Pushkara LIS | 75.235 | 28.694 | 0 | 28.689 | 38.13
4. | Tadipudi LIS | 83.609 | 29.263 | 0 | 29.263 | 35.00
5. | Taraka Thirtha Sagaram Reservoir | 10.000 | 5.649 | 0 | 5.649 | 56.49
6 | Sardar Gouthu Lachanna Thotapali Barrage Project | 45.704 | 16.566 | 0 | 16.566 | 22.25
7. | Yerracalva | 9.996 | 4.072 | 0 | 4.072 | 40.74
 | TOTAL | 266.108 | 87.493 |  | 87.488 | 29.49
(CCA in Th. ha.)
7th PIRC Meeting (11th September 2020):
Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 216
MUSURUMILLI

## Slide 218
Yerracalva project

## Slide 219
PUSHKARA LIS

## Slide 220
Pushkara LIS

## Slide 222
Key Reasons For Progress Delays
Status | Key Reason
X | Absence of Hydraulic Connectivity up to Outlet.
√ | Delay in Govt/Administrative clearances.
X | State budget constraints.
X | Unwillingness of farmers.
√ | Delays in tendering.
√ | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
7th PIRC Meeting (11th September 2020):
Progress Review Presentations

## Slide 223
STATUS OF CADWM WORKS
Survey, Planning and Design works are completed for the projects Gundlakamma,
Yerracalva.
Survey, Planning and Design works are in progress for the project Thotapalli.
Tenders for Survey, Planning and Design for the projects Pushkara and Musurimilli are invited and agency is fixed. Due to rainy season work is not yet started.
Administrative Sanction for Structural and Non- structural components are issued by Govt. of A.P for the projects Musurumilli, Pushakara and Yerracalva projects.
Administrative Sanction for Structural and Non- structural components for the projects Gundlakamma & Tadipudi is under consideration with Govt. of A.P.

## Slide 224: -THANKS-

## Slide 225
BIHAR
Presentation
for
7th Meeting of PIRC for CADWM
(11th September’ 2020)

## Slide 226
Bihar
Number of Projects : 2 Projects Included: 1 Projects Availing CA: 1 Projects Reporting Progress:1
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | Balance CCA (in th. Ha.) | WUA (Nos)
Target | 142.39 | 50.66 | 30.51 | 2
Progress | 42.84 | 35.82 | 13.703 | 0
Physical Progress
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 227
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  |  | 
 |  |  | Up to 2017-18 | 2018-19 | 2019-20 | 2020-21(up to August’2020) | Total | % Progress | Target for 2020-21
1 | Durgawati | 32.24 | 9.470 | 3.998 | 2.625 | 1.160 | 17.253 | 53.51% | 15.720
 | TOTAL | 32.24 | 9.470 | 3.998 | 2.625 | 1.160 | 17.253 | 53.51% | 15.720
( Area in Th. Ha.)
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 228
WUAs Progress
Sr. No. | Project | Formation of WUAs (Target) | WUA Created | WUAs Registered |  |  |  |  | Target | Handed Over to WUAs | Functional grant given
 |  |  |  | Up to 2017-18 | 2018-19 | 2019-20 | 2020-21 (up to Aug’2020) | Total | 2020-21 |  | 
1 | Durgawati | 30 | 14 | - | - | 10 | 2 | 12 | 16 | 9 | -
 | TOTAL | 30 | 14 | - | - | 10 | 2 | 12 | 16 | 9 | -
(WUAs in Nos)
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 229
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  |  | Target
 |  |  | Up to 2017-18 | 2018-19 | 2019-20 | 2020-21 (up to Aug’2020) | Total | % Progress | 2020-21
1 | Durgawati | 55.57 | 26.3 | 14.42 | - | - | 40.72 | 73.27% | 14.85
 | TOTAL | 55.57 | 26.3 | 14.42 | - | - | 40.72 | 73.27% | 14.85
(CA in Rs. Crore)
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 230
Micro Irrigation Progress
Sr. No. | Project | CCA under M.I. (Target) | Area covered under infrastructure development for M.I. |  |  |  |  | %Progress | Target
 |  |  | Up to 2017-18 | 2018-19 | 2019-20 | 2020-21 (up to Aug’2020) | Total |  | 2020-21
1 | Durgawati | 3.247 | - | 0.200 | - | - | 0.200 | 6.15% | 3.047
 | TOTAL | 3.247 | - | 0.200 | - | - | 0.200 | 6.15% | 3.047
( Area in Th. Ha.)
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 231
Financial Progress
Sr. No. | Project | Total Expenditure Target | Financial Progress |  |  |  |  |  | Balance Target
 |  |  | Up to 2017-18 | 2018-19 | 2019-20 | 2020-21 (up to Aug’2020) | Total | %Progress | 2020-21
1 | Durgawati | 148.57 | 34.21 | 17.55 | 11.53 | 3.24 | 66.53 | 44.78% | 84.04
 | TOTAL | 148.57 | 34.21 | 17.55 | 11.53 | 3.24 | 66.53 | 44.78% | 84.04
(In Rs. Crore)
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 232
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Durgawati | 32.467 | 1.960 | 15.52 | 17.48 | 53.83% | 39.61 | 27.00 | 68.16
 | TOTAL | 32.467 | 1.960 | 15.52 | 17.48 | 53.83% | 39.61 | 27.00 | 68.16
(CCA in Th. ha.)
* i.e. CCA developed up to 31-03-2016 under CADWM also includes CCA developed of 227 Ha before CADWM inclusion.
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 233
Physical /Financial Targets for 2020-21
Sl. No. | Components | Unit | Rate (in lakh) | Target as per Approved DPR |  | Available amount | Progress Up to March’ 2020 |  | Target for 2020-21 | 
 |  |  |  | Physical | Financial |  | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | Survey, Planning & Design | Ha. | 0.012 | 36778 | 441.336 | 127.4 | 0 | 0.000 | 10616 | 127.4
2 | OFD Works |  |  |  |  |  |  |  |  | 
 | (i) OFD Works Field Channel (Lined) | Ha. | 0.3678 | 29220 | 10747.23 | 10748.48 | 16320 | 5274.915 | 12900 | 5472.315
 | (ii) Micro-Irrigation | Ha. | 0.50 | 3247 | 1623.50 | 813.220 | 200 | 151.56 | 3047 | 1471.94
3 | Field, Intermediate and Link Drains | Ha. | 0.06 | 6500 | 390.00 | 0.00 | 0 | 0.000 | 0 | 0.00
4 | Software Activities |  |  |  |  |  |  |  |  | 
(i) | Training |  |  |  |  |  |  |  |  | 
 | (a) State Level | Each | L.S. | 5 | 7.50 | 6.660 | 24 | 7.706 | 11 | 3.238
 | (b) Project Level | Each | L.S. | 25 | 5.00 |  |  |  |  | 
(ii) | Monitoring & Evaluation | L.S. | L.S. |  | 25.00 | 5 |  | 5.369 |  | 2.6845
(iii) | Demonstration |  |  |  |  |  |  |  |  | 
 | (a) Kharif | Each | L.S. | 500 | 11.96 | 17.96 | 0 | 0.000 | 1000 | 28.22
 | (b) Rabbi | Each | L.S. | 500 | 16.26 |  |  |  |  | 
5 | (i) One time Functional grant to WUAs | Ha. | 0.012 | 32467 | 389.64 | 192.00 | 0 | 0.000 | 32467 | 389.64
 | (ii) One time Infrastructure grant to WUAs | Per WUA | 3.00 | 2 | 6.00 | 0.00 | 0 | 0.000 | 30 | 90.00
6 | One time grant to WALMI | L.S. | L.S. | - | 10.00 | 0.00 | - | 0.000 | 0 | 0.00
7 | CAD & WM Establishment |  |  |  | 1276.07 | 818.88 |  | 946.3908 |  | 329.6792
 |  | Total |  |  | 14949.49 | 12729.60 |  | 6385.9408 |  | 7915.1167
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 234
Issues
Construction of Lined Field Channels:-
No Land acquisition is involved. Construction of field channels is being done on farmers’ land.
Average land holding being very small (Avg. 0.4 Ha.), hence farmers are not interested in giving their valuable land for construction of field channels.
Limited period for execution of works.
Due to crops in the field, the working period for construction of field is available only between the month of April to June.
Construction work of some of the distributaries has not been started yet due to land acquisition issues.
Due to prevalence of COVID-19 Pandemic and subsequent lockdowns the progress of CADWM works suffered badly during working period from April –June 2020.
Local Public Hindrance.
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 235
Issues
Micro Irrigation:-
Cost norm for infrastructure development (pump house, sump, filtration unit, main & sub-main pipe line, outlet etc.) of Micro irrigation as per provision in guideline is only Rs. 50,000/- Ha. where actual cost is Rs.1,16,000/- Ha., this needs enhancement.
Easy availability of water for growing traditional crops like paddy and wheat. So farmers are reluctant to Micro Irrigation for growing vegetables, flowers etc.
Small & Fragmented Land Holding
91% of farmers of Bihar are small & marginal farmers with average land
holding of 0.4 Ha.
Scarcity of capital
Average cost of providing drip irrigation system to famers in Bihar is approx. Rs. 1,30,000/- Ha. + 12% GST.
To promote micro irrigation total subsidy offered by Govt. is 90% of the basic cost.
GST (@ 12%) & balance 10% of the basic cost of the drip system which amounts to be approx.. Rs. 28600/- Ha. has to be borne by the farmers.
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 236
Issues
Marginal & Small farmers are not taking interest due to high farmers’ share i.e. Rs. 28600/- Ha.
Sub-letting of Plots
Owners of plots sublet their plots to other small farmers on lump sump contract so the owners do not show interest for making investment in Micro irrigation.
Conjunctive use of Water
Farmers demand tube wells to supplement canal water for assured availability of water during lean season.
Inadequate Storage & Transport facility for produce
Poor Agriculture marketing services.
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 237
Extra Slides
{ Project-specific information}
The construction of Lined field channels in about 1840 Ha. area of CCA is under progress.
Farmers are being motivated to adopt Micro irrigation.
The construction of remaining canal system needs to be completed at the earliest so that work of CADWM may be expedited.
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 238
Glimpses Of Project Progress
Index Map for Durgawati CADWM Project
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 239: Schematic Diagram for Kudra Weir System under Durgawati Reservoir Project
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 240: Schematic Diagram Showing the Land Acquisition Issues in Durgawati Reservoir Project
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 241
Photographs for Field Channels and Infrastructure for Micro Irrigation.
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 242
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 243
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 244
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 245
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 246
THANKS………
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 247
Jharkhand
Number of Projects : 1 Projects Included: 1 Projects Availing CA: 0 Projects Reporting Progress:0
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | Balance CCA (in th. Ha.) | WUA (Nos)
Target | 747.53 | 133.32 | 66.645 | 256
Progress | 0 | 0 | 0 | 0
Physical Progress
7th PIRC Virtual Meeting (11th Sept2020): Progress Review Presentations

## Slide 248
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | 2017-18 | 2018-19 | 2019-20 | Total | % Progress |  | 
1 | Subarnarekha Multipurpose | 66.645 | 0 | 0 | 0 | 0 | 0 | 15.0 | 51.645
 | TOTAL | 66.645 | 0 | 0 | 0 | 0 | 0 | 15.0 | 51.645
( Area in Th. Ha.)
7th PIRC Virtual Meeting (11th Sept2020): Progress Review Presentations
Target will be Revised after getting AA from GOJ

## Slide 249
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | Before April 2017 | 2017-18 | 2018-19 | 2019-20 | Total | % Progress |  | 
1 | Subarnarekha Multipurpose | 256 | 0 | 0 | 0 | 48 | 0 | 19 | 106 | 102
 | TOTAL | 256 | 0 | 0 | 0 | 48 | 0 | 19 | 106 | 102
(WUA’s in No’s)
7th PIRC Virtual Meeting (11th Sept2020): Progress Review Presentations
Target will be Revised after getting AA from GOJ

## Slide 250
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | 2017-18 | 2018-19 | 2019-20 | Total | % Progress |  | 
1 | Subarnarekha Multipurpose | 133.32 | 0 | 0 | 0 | 0 | 0 | 50.00 | 83.32
 | TOTAL | 133.32 | 0 | 0 | 0 | 0 | 0 | 50.00 | 83.32
(CA in Rs. Crores)
7th PIRC Virtual Meeting (11th Sept2020): Progress Review Presentations
Target will be Revised after getting AA from GOJ

## Slide 251
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | 2017-18 | 2018-19 | 2019-20 | Total | % Progress |  | 
1 | Subarnarekha Multipurpose Project | 747.53 | 0 | 0 | 0 | 0 | 0 | 65.00 | 300.00
 | TOTAL | 747.53 | 0 | 0 | 0 | 0 | 0 | 65.00 | 300.00
(TE in Rs. Crores)
7th PIRC Virtual Meeting (11th Sept2020): Progress Review Presentations
Target will be Revised after getting AA from GOJ

## Slide 252
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2017 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Subarnarekha Multipurpose | 66.645 | 0 | 0 | 0 | 0 | 236.85 | 107.33 | 45.31
 | TOTAL | 66.645 | 0 | 0 | 0 | 0 | 236.85 | 107.33 | 45.31
(CCA in Th. ha.)
7th PIRC Virtual Meeting (11th Sept2020): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2017) and before CADWM inclusion.

## Slide 253
Key Reasons For Progress Delays
Status | Key Reason
√ | Delay in Administrative clearances.-Administrative Approval for Rs747.53 cr is in process of Approval
√ | State budget constraints- so far no provision of Budget for CADWM in 2020-21
7th PIRC Virtual Meeting (11th Sept2020): Progress Review Presentations

## Slide 254
THANKS………
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 255
7th PIRC Meeting : Progress Review Presentations
7th Project Implementation Review Committee (PIRC) for CADWM Implementation (on 11.9.2020)
Presentation on CADWM Works
Uttar Pradesh
By
Chief Engineer, UGBO, CWC
Lucknow

## Slide 256: PROJECTS UNDER CADWM PROGRAMME
S. No. | PROJECT | TOTAL CCA OF PROJECT (Th. Hectare) | ESTIMATED COST (Cr.) | REMARK
1 | Saryu Nahar Pariyojna Ph-III | 480.000 | 1672.70 | 
2 | Arjun Sahayak Pariyojna | 44.381* | 188.96 | 
3 | Madhya Ganga Canal PH-II | 146.000 | 510.65 | DPR of CAD works along with compliances by State Govt. sent to CE, PMO, CWC further necessary action for its inclusion in CADWM
7th PIRC Meeting : Progress Review Presentations
*DPR was submitted for 54.087 which included 9.706 th. ha CCA of old system. However, the approval
was granted for 44.381 th. ha.

## Slide 257
PHYSICAL & FINANCIAL PROGRESS
Number of Projects : 3 Projects Included: 2 Projects Availing CA: 2 Projects Reporting Progress:1
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | Balance CCA (in th. Ha.) | WUA (Nos)
Target | 1861.67 | 917 | 524.381 | 1068
Progress | 0 | 0 | 0 | 0
Physical Progress
7th PIRC Meeting : Progress Review Presentations
0.47
156

## Slide 258
CA RELEASE PROGRESS
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  | Target for 2020-21
 |  |  | 2019-20 | 2020-21 | Total | % Progress | 
1 | Saryu Nahar Pariyojna Ph-III | 837.06 | 150 | 0 | 150.00 | 18.00 | 250.26
2 | Arjun Sahayak Pariyojna | 79.94 | 0 | 6.00 | 6.00 | 7.50 | 50.05
3 | Madhya Ganga Canal PH-II | 0 | 0 | 0 | 0 | 0 | -
 | TOTAL | 917 | 150 | 6.00 | 156.00 | 25.5 | 300.31
(CA in Rs. Crores)
7th PIRC Meeting : Progress Review Presentations

## Slide 259
TOTAL EXPENDITURE PROGRESS
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  | Target for 2020-21
 |  |  | 2019-20 | 2020-21 | Total | % Progress | 
1 | Saryu Nahar Pariyojna Ph-III | 1672.70 | 0.470 | 0 | 0.470 | 0 | 500.00
2 | Arjun Sahayak Pariyojna | 188.96* | 0 | 0 | 0 | 0 | 100.00
3 | Madhya Ganga Canal PH-II | 0 | 0 | 0 | 0 | 0 | -
 | TOTAL | 1861.66 | 0.470 | 0 | 0.470 | 0 | 600.00
(TE in Rs. Crores)
7th PIRC Meeting : Progress Review Presentations
*Expenditure against CCA of 44.381 th. ha.

## Slide 260
CCA PROGRESS
Sr. No. | Project | Total CCA | CCA Progress |  |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | 2019-20 | 2020-21 | Total | % Progress |  | 
1 | Saryu Nahar Pariyojna Ph-III | 480.000 | 0 | 0 | 0 | 0 | 144.000 | 144.000
2 | Arjun Sahayak Pariyojna | 44.381 | 0 | 0 | 0 | 0 | 28.750 | 12.668
3 | Madhya Ganga Canal PH-II |  | 0 | 0 | 0 | 0 | Yet to be included in CADWM | -
 | TOTAL | 524.381 | 0 | 0 | 0 | 0 |  | 
( Area in Th. Ha.)
7th PIRC Meeting : Progress Review Presentations
Note- Balance area will be taken in next FY 2022-23.

## Slide 261
WUA PROGRESS
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2020-21
 |  |  | Before April 2016 | 2016-19 | 2019-20 | 2020-21 | Total | % Progress | 
1 | Saryu Nahar Pariyojna Ph-III | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 
2 | Arjun Sahayak Pariyojna | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 
3 | Madhya Ganga Canal PH-II | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 
 | TOTAL | 1068 | 0 | 0 | 0 | 0 | 0 | 0 | 
(WUA’s in No’s)
7th PIRC Meeting : Progress Review Presentations
Note :- Formation of WUA is being done by Irrigation Department (U.P.)

## Slide 262
BROAD REVIEW
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2019 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Saryu Nahar Pariyojna Ph-III | 480.000 | 0 | 0 | 0 | 0 | 473.00 | 313 | 66.17
2 | Arjun Sahayak Pariyojna | 44.381 | 0 | 0 | 0 | 0 | 44.38 | 30 | 67.59
3 | Madhya Ganga Canal PH-II | 0 | 0 | 0 | 0 | 0 | 146.53 | - | 
 | TOTAL | 534.087 | 0 | 0 | 0 | 0 | 663.91 | 343 | 
(CCA in Th. ha.)
7th PIRC Meeting : Progress Review Presentations
CCA developed under CADWM (up to Aug 2020) and before CADWM inclusion.

## Slide 263
Broad Reasons For Progress Delays
Status | Key Reason
√ | Delay in Govt/Administrative clearances.
√ | Delays in tendering.
7th PIRC Meeting : Progress Review Presentations

## Slide 266
G.C.A. : 255225 Ha.
C.C.A. : 225433 Ha.
I.P.C. : 59000 Ha.(Dry)

## Slide 269
11 September, 2020
PUNJAB WATER RESOURCES MANAGEMENT & DEVELOPMENT CORPORATION (PWRM&DC)
Status of
PMKSY- CAD&WM Works
For
Kotla Branch Part-II, CADWM Project, Punjab

## Slide 270
Punjab Water Resources Management & Development Corporation, Punjab
No. of Projects:1 (Kotla Branch Part-II, CADWM Project) Project Availing CA: 1 Availed CA Till Now: 18.08 Crore (credit to PWRMDC by State govt is underprocess) Financial Progress Targets: 477.19 Crore Financial Progress Achieved: NIL Physical Progress CCA Targets: 142.658 Thousand Hectare Physical Progress Achieved: NIL
7th PIRC Meeting : Progress Review Presentations

## Slide 271: Estimated Cost of CAD Works
Total Cost | Central Share | State Share | Farmer’s Share
477.19 Crore | 228.87 Crore | 246.61 Crore | 1.71 Crore
7th PIRC Meeting : Progress Review Presentations

## Slide 272
Year Wise Physical Targets
Sr. No. | Project | CCA Balance Target | CCA Target |  | 
 |  |  | 2020-21 | 2021-22 | Total
1 | Kotla Branch Part-II Project | 142.658 | 49.93 | 92.728 | 142.658
( Area in Th. Ha.)
7th PIRC Meeting : Progress Review Presentations

## Slide 273
Year wise Financial Requirements
Sr. No. | Project | Amount | Financial Requirements |  | 
 |  |  | 2020-21 | 2021-22 | Total
1 | Kotla Branch Part-II Project | 477.19 | 167.01 | 310.18 | 477.19
(Amount in Crore)
7th PIRC Meeting : Progress Review Presentations

## Slide 274: 7th PIRC Meeting : Progress Review Presentations
Micro Irrigation
10% of Total Project Area has been included.
Component | CCA (In Thousand Hectare) | Total Cost (In Crore) | Central Share (In Crore) | State Share (In Crore)
Micro Irrigation Infrastructure including components of sump, pump, HDPE Pipelines and pertinent devices | 14.2658 | 71.33 | 35.6645 | 35.6655

## Slide 275: Districts to be Benefitted
Bathinda
Mansa
Sangrur
Barnala
7th PIRC Meeting : Progress Review Presentations

## Slide 276: No. of WUA’s Constituted = 967 No. of WUA’s Registered = 967 Area Covered = ---- No. of WUA’s actually functioning as on 01.01.2020 = 967
Water User Association’s (WUA’s)
7th PIRC Meeting : Progress Review Presentations

## Slide 277
Key Reasons For Progress Delays
Status | Key Reason
X | Absence of Hydraulic Connectivity up to Outlet.
X | Delay in Govt/Administrative clearances.
√ | State budget constraints.
√ | Disputes/Delay in proceeding regarding finalisation of watercourses scheme as per Canal & Drainage Act 1873.
X | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
√ | Imposition of curfew/lockdown by State Govt. Due to pandemic.
7th PIRC Meeting : Progress Review Presentations

## Slide 278
THANKS………
7th Meeting of PIRC for CADWM (11th Sept’2020)

## Slide 279
Power Point Presentation
for the meeting to be held on 11-09-2020 under the Chairmanship of Secretary (DoWR, RD & GR), Govt. of India to review the progress of Command Area Development works of 99 prioritized projects.
Jammu & Kashmir (UT)

## Slide 280
Physical and Financial Targets for 2019-20 & 2020-21
State Name | Project Name | Physical Targets 2019-20 (Th. Ha.) | Financial targets 2019-20 (Rs. Lakhs) |  | TOTAL | Physical Targets 2020-21 (Th. Ha.) | Financial targets 2020-21 (Rs. Lakhs) |  | TOTAL
 |  |  | S.S | C.S |  |  |  |  | 
 |  |  |  |  |  |  | S.S | C.S | 
Jammu & Kashmir | (Inclusion No.N.19011/52/2017-CADWM-362-378 Dtd.26-02-2018) Tral Lift Irrigation Scheme | 0.606 | 111.96 | 122.76 | 234.72 | 0.361 | 109.98 | 102.35 | 212.33
 | (Inclusion No.N.19011/53/2017-CADWM-319-334 Dtd.20-02-2018) Rajpora Lift Irrigation Scheme | 0.285 | 141.333 | 67.113 | 208.446 | 0 | 0.00 | 0.00 | 0.00

## Slide 281
State, Project and Year-wise CCA Progress
State Name | Project Name | Project Total CCA (Th.Ha.) | Balance Outstanding CCA as on 01 April 2016 (Th.Ha.) | 2016-17 (Th.Ha.) | 2017-18 (Th.Ha.) | 2018-19 (Th.Ha.) | 2019-20 (Th.Ha.) | Total CCA Progress | % of CCA Progress
Jammu & Kashmir | Rajpora Lift Irrigation Scheme | 1.620 | 0.585 | 0 | 0 | 0.300 | 0.263 | 0.563 | 97%
 | Tral Lift Irrigation Scheme | 3.415 | 1.413 | 0 | 0 | 0.500 | 0.400 | 0.900 | 63%

## Slide 282
State and Year-wise CCA Progress
S.No. | State Name | Project Total CCA (Th.Ha.) | Balance Outstanding CCA as on 01 April 2016 (Th.Ha.) | 2016-17 (Th.Ha.) | 2017-18 (Th.Ha.) | 2018-19 (Th.Ha.) | 2019-20 (Th.Ha.) | Total CCA Progress | % of CCA Progress
01. | Jammu & Kashmir | 5.035 | 1.998 | 0 | 0 | 0.800 | 0.463 | 1.263 | 63%

## Slide 283
Project and Year-wise Number of WUA Targeted, Created and Registered
State Name | Project | No. of Targeted WUA | No. of WUA Created | 2016-17 | 2017-18 | 2018-19 | 2019-20
Jammu & Kashmir | Tral Lift Irrigation Scheme | 3 | 1 | 0 | 0 | 1 | 0
 | Rajpora Lift Irrigation Scheme | 2 | 1 | 0 | 0 | 1 | 0

## Slide 284
State, Project and Year-wise Financial Progress
State Name | Project Name | Target (Rs. Lakhs) | 2016-17 (Rs. Lakhs) | 2017-18 (Rs. Lakhs) | 2018-19 (Rs. Lakhs) | 2019-20 (Rs. Lakhs) | Total Financial Progress | % of Financial Progress
Jammu & Kashmir | Rajpora Lift Irrigation Scheme | 361.28 | 0 | 0 | 154.00 | 122.00 | 276.00 | 76%
 | Tral Lift Irrigation Scheme | 616.07 | 0 | 0 | 169.00 | 135.00 | 304.00 | 49%

## Slide 285
State and Year-wise Financial Progress
S.No. | State Name | Target (Rs. Lakhs) | 2016-17 (Rs. Lakhs) | 2017-18 (Rs. Lakhs) | 2018-19 (Rs. Lakhs) | 2019-20 (Rs. Lakhs) | Total Financial Progress | % of Financial Progress
01. | Jammu & Kashmir | 977.35 | 0 | 0 | 323.00 | 193.00 | 516.00 | 52%

## Slide 286
State, Project and Year-wise CA Released
State Name | Project Name | Targeted CA (Rs. Lakhs) | 2015-2016 (Rs. Lakhs) | 2016-17 (Rs. Lakhs) | 2017-18 (Rs.Lakhs) | 2018-19 (Rs. Lakhs) | 2019-20 (Rs. Lakhs) | Total CA Release | % of CA Release Progress
Jammu & Kashmir | Rajpora Lift Irrigation Scheme | 152.12 | 0 | 0 | 0 | 85.00 | 37.00 | 122.00 | 80%
 | Tral Lift Irrigation Scheme | 301.07 | 0 | 0 | 0 | 64.00 | 71.00 | 135.00 | 44%

## Slide 287
State and Year-wise CA Released
S.No. | State Name | 2016-17 (Rs. Lakhs) | 2017-18 (Rs. Lakhs) | 2018-19 (Rs. Lakhs) | 2019-20 (Rs. Lakhs)
01. | Jammu and Kashmir | 0 | 0 | 149.00 | 108.00

## Slide 288
Project and Year-wise MI Progress
State Name | Project Name | Targeted MI (Th. Ha.) | CA Targeted For MI (Rs.) | MI works under taken (as per CA Proposed) |  |  | Progress CCA | % of MI Progress
 |  |  |  | 2016-17 (Th.Ha.) | 2017-18 (Th.Ha.) | 2018-19 (Th.Ha.) |  | 
Jammu & Kashmir | Rajpora Lift Irrigation Scheme | 0.058 | 14.50 | 0.00 | 0.00 | 0.06 | 0.018 | 31%
 | Tral Lift Irrigation Scheme | 0.141 | 35.25 | 0.00 | 0.00 | 0.04 | 0.035 | 24.82%

## Slide 289
Bottle Necks
In adequate and untimely release of funds which effects physical as well as financial progress.

## Slide 296
Thanks

## Slide 297
Power Point Presentation
for the meeting to be held under the Chairmanship of Secretary (MoWR, RD & GR), Govt. of India to review the progress of Command Area Development works of 99 prioritized projects.
Ladakh(UT)

## Slide 298: Status of Project Inclusion under CAD Prograame
The Parkachik –Khawas Command Area has been served (up to 2016-17) under New CAD & Water Management Project Kargil sanctioned vide Govt. of India Letter No:13-5/2010-CADWM/3779-FTS dated 19.10.2011
Year of Start: 2011-12
The Project has been included under CADWM Programme of MoWR, RD&GR vide letter no. 19011/53/2017-CADWM/387-402 dated 28/02/2018
Total Cost of Project: Rs 186.550 lakh (Central Share: Rs70.913 lakh State Share:Rs 115.637 lakh)

## Slide 299
Physical and Financial Targets for 2019-20 & 2020-21
State Name | Project Name | Physical Targets 2019-20 (Th. Ha.) | Financial targets 2019-20 (Rs. Lakhs) |  | TOTAL | Physical Targets 2020-21 (Th. Ha.) | Financial targets 2020-21 (Rs. Lakhs) |  | TOTAL
 |  |  | S.S | C.S |  |  |  |  | 
 |  |  |  |  |  |  | S.S | C.S | 
Ladakh | (Inclusion No. MoWR, RD&GR vide letter no.19011/53/2017/CADWM/ 387-402 dated 28/02/2018) Parkachik Khawas Irrigation CAD ProjectS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 300
State, Project and Year-wise CCA Progress
State Name | Project Name | Project Total CCA (Th.Ha.) | Balance Outstanding CCA as on 01 April 2016 (Th.Ha.) | 2016-17 (Th.Ha.) | 2017-18 (Th.Ha.) | 2018-19 (Th.Ha.) | 2019-20 (Th.Ha.) | Total CCA Progress | % of CCA Progress
Ladakh | Parkachik Khawas Irrigation CAD ProjectS | 0.462 | 0.462 | 0 | 0 | 0.231 | 0 | 0.231 | 50%

## Slide 301
State and Year-wise CCA Progress
S.No. | State Name | Project Total CCA (Th.Ha.) | Balance Outstanding CCA as on 01 April 2016 (Th.Ha.) | 2016-17 (Th.Ha.) | 2017-18 (Th.Ha.) | 2018-19 (Th.Ha.) | 2019-20 (Th.Ha.) | Total CCA Progress | % of CCA Progress
01. | Ladakh | 0.462 | 0.462 | 0 | 0 | 0.231 | 0 | 0.231 | 50%

## Slide 302
Project and Year-wise Number of WUA Targeted, Created and Registered
State Name | Project | No. of Targeted WUA | No. of WUA Created | 2016-17 | 2017-18 | 2018-19 | 2019-20
Ladakh | Parkachik Khawas Irrigation CAD ProjectS | 1 | 0 | 0 | 0 | 0 | 0

## Slide 303
State, Project and Year-wise Financial Progress
State Name | Project Name | Target (Rs. Lakhs) | 2016-17 (Rs. Lakhs) | 2017-18 (Rs. Lakhs) | 2018-19 (Rs. Lakhs) | 2019-20 (Rs. Lakhs) | Total Financial Progress | % of Financial Progress
Ladakh | Parkachik Khawas Irrigation CAD Projects | 1.8655 | 0 | 0 | 0.21 | 0 | 0.21 | 11%

## Slide 304
State and Year-wise Financial Progress
S.No. | State Name | Target (Rs. Lakhs) | 2016-17 (Rs. Lakhs) | 2017-18 (Rs. Lakhs) | 2018-19 (Rs. Lakhs) | 2019-20 (Rs. Lakhs) | Total Financial Progress | % of Financial Progress
01. | Ladakh | 1.8655 | 0 | 0 | 0.21 | 0 | 0.21 | 11%

## Slide 305
State, Project and Year-wise CA Released
State Name | Project Name | Targeted CA (Rs. Lakhs) | 2015-2016 (Rs. Lakhs) | 2016-17 (Rs. Lakhs) | 2017-18 (Rs.Lakhs) | 2018-19 (Rs. Lakhs) | 2019-20 (Rs. Lakhs) | Total CA Release | % of CA Release Progress
Ladakh | Parkachik Khawas Irrigation CAD Projects | 0.7191 | 0 | 0 | 0 | 0.21 | 0 | 0.21 | 29.62%

## Slide 306
State and Year-wise CA Released
S.No. | State Name | 2017-18 (Rs. Lakh) | 2018-19 (Rs. Lakh) | 2019-20 (Rs. Lakh) | 2020-21 (Rs. Lakh)
01. | Ladakh | 0 | 0.21 | 0 | 0

## Slide 307
Project and Year-wise MI Progress
State Name | Project Name | Targeted MI (Th. Ha.) | CA Targeted For MI (Rs.) | MI works under taken (as per CA Proposed) |  |  | Progress CCA | % of MI Progress
 |  |  |  | 2016-17 (Th.Ha.) | 2017-18 (Th.Ha.) | 2018-19 (Th.Ha.) |  | 
Ladakh | Parkachik Khawas Irrigation CAD Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0%

## Slide 308
Bottle Necks
In adequate and untimely release of funds which effects physical as well as financial progress.

## Slide 309: Terrain near canal headworks

## Slide 310: Suru River : Source of Parkachik Khawas Irrigation Canal

## Slide 311: Command Areas under Parkachik Khawas canal

## Slide 312: Field Channel

## Slide 313: CAD activities under Parkachik Khawas Canal ( Field Drain )

## Slide 314: Field Channel

## Slide 315
Thanks

## Slide 316
Kerala
Number of Projects : 1 Projects Included: 1 Projects Availing CA: 1 Projects Reporting Progress:1
7th PIRC Meeting Progress Review Presentations
Chart: 
| Total Expenditure (RS.Crores) | CA(RS.Crores) | Balance CCA (in th .Ha) | WUA (Nos)
Target | 107 | 48.71 | 16.795 | 240
Progress | 11.07 | 3.68 | 0.60371 | 114
107
*0.99 Cr CA released in March 2016 and 2.69 Cr CA released in 2020-21

## Slide 317
CCA Progress
Sl. No. | Project | Target | Upto March 2016 | Balance CCA Target | CCA Progress |  |  |  |  |  | % Progress | Target for 2020-21 | Target for 2021-22
 |  |  |  |  | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 August 2020 | Total upto August 2020 |  |  | 
1 | Muvattupuzha | 18.476 | 1.681 | 16.795 | 0 | 0 | 0 | 0.33636 | 0.26735 | 2.285 | 12.36 | 2.702 | 13.49
( Area in Th. Ha.)
7th PIRC Meeting Progress Review Presentations

## Slide 318
WUA Progress
Sl. No. | Project | WUA Target | WUA Progress |  |  |  |  |  |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | Upto March 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 Upto Aug 2020 | Total | % Progress |  | 
1 | Muvattupuzha | 240 | 95 | 0 | 0 | 19 | 0 | 0 | 114 | 47.50 | 32 | 94
(WUA’s in No’s)
7th PIRC Meeting Progress Review Presentations

## Slide 319
CA Release Progress
Sl. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  |  |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | Up to 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Total | % Progress |  | 
1 | Muvattupuzha | 48.71 | 0.99 | 0 | 0 | 0 | 0 | 2.69 | 3.68 | 7.55 | 5.00 | -
(CA in Rs. Crores)
7th PIRC Meeting Progress Review Presentations

## Slide 320
Total Expenditure Progress
Sl. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  |  |  |  | Target for 2020-21 | Target for 2021-22
 |  |  | Up to 2016 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 Upto Aug 2020 | Total | % Progress |  | 
1 | Muvattupuzha | 107.29 | 9.5357 | 1.5441 | 0 | 0 | 0 | 0 | 11.07 | 10.32 | 10.16 | -
(TE in Rs. Crores)
7th PIRC Meeting Progress Review Presentations

## Slide 321
Broad Review
Sl. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Muvattupuzha | 18.476 (FIC:16.576 & MI:1.900) | 1.681 | 0.60371 | 2.28471 | 12.36 | 30.719 | 28.648 | 93.25
(CCA in Th. ha.)
* i.e. 1681 ha CCA developed under CADWM up to 31-03-2016
7th PIRC Meeting Progress Review Presentations

## Slide 322
MICRO-IRRIGATION WORKS
In approved DPR of CADWM, 1900 ha has been allotted for Micro Irrigation.
* In MVIP , 5 micro irrigation projects are approved for the year 2019-20 for an amount of 306 lakhs to achieve 526 Ha ayacut. DPR preparation are in progress.(civil works only)
* For the year of 2020-21 ,1 no of work(Drip Irrigation to Koottathinal) proposed for 527 lakhs to achieve 82.3 Ha ayacut.(Including Civil/Electrical/Mechanical works)

## Slide 323
LIST OF CADWM NEW WORKS for 2020-21
23 nos of works proposed for an amount of Rs.10.165Cr,includes:
  8 Nos. of field channel -1.209824 Cr - 432 Ha
  3 No. of Surface drain - 0.28224 Cr - 126Ha
  11 Nos. of System correction -3.403456 Cr - 4000Ha
  1 No. of Micro Irrigation - 5.27Cr - 82.30Ha

## Slide 324
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
√ | Delay in Govt/Administrative clearances.
√ | State budget constraints.
√ | Unwillingness of farmers.
√ | Delays in tendering.
√ | Other Issue (to be specified).
7th PIRC Meeting Progress Review Presentations

## Slide 325
Key Reasons For Progress Delays
√ | Other Issues
1. | Muvattupuzha Valley Irrigation Project passing through Ghat areas. Due to the undulated topography, 100% efficiency can not be attained, as per the present norms of CADWM
2. | High labour cost.
3. | Changes in the climatic conditions and cropping pattern.
4. | As the value of land is high in this region, people are not willing to surrender land at free of cost.
7th PIRC Meeting Progress Review Presentations

## Slide 326
Completed works

## Slide 327
Field channel constructed at ch 34750m of LBMC
Field channel constructed at ch 1100m of Kurukunnapuram MD
CADA works completed
Notes: CADA wprks completed

## Slide 328
Mamalassery distributory CADA works
Notes: 328
Mammalassery distributory CADA works

## Slide 329
Notes: 329